Before the hon’ble Central Electricity regulatory Commission

New Delhi

Petition No. 	    /MP/2026

In the matter of:             	Petition under Section 79(1)(c) of the Electricity Act 2003 read with Regulation 13(2)(h) of the CERC (Sharing of Inter-State Transmission Charges and Losses) Regulations 2020 (as amended) seeking suitable directions and orders pursuant to findings in the Report dated 11.06.2026 of the Committee constituted vide Office Order dated 30.07.2025 read with Addendum dated 14.01.2026 extending the Scheduled Commercial Operation Date of the commissioned capacity of the Petitioners’ 470 MW Hybrid Project in Gadag, Karnataka thereby maintaining eligibility for waiver from payment of full ISTS transmission charges.

AND

IN THE MATTER OF:

1. 	Serentica Renewables India 3 Private Limited

Through its Authorised Representative

Regd. Office – RMZ infinity, 5th Floor,

Plot No. 15, Udyog Vihar, Phase IV,

Gurugram, Haryana - 122015

Email: ravi.kalra@serenticaglobal.com /

regulatory@serenticaglobal.com

Phone: +91 97168 08746                                                      …Petitioner No. 1

2. 	Serentica Renewables India Private Limited

Through its Authorised Representative

Regd. Office – RMZ infinity, 5th Floor,

Plot No. 15, Udyog Vihar, Phase IV,

Gurugram, Haryana - 122015

Email: ravi.kalra@serenticaglobal.com /

regulatory@serenticaglobal.com

Phone: +91 97168 08746                                                      …Petitioner No. 2

Versus

1. 	Central Transmission Utility of India Limited

Through its Chairman

“Saudamini”, 1st Floor, Plot No. 2

Sector 29, Gurugram, Haryana – 122001

Phone No: 7042396704

Email – swapnilverma@powergrid.in                                          …Respondent

PETITION UNDER SECTION 79(1)(C) OF THE ELECTRICITY ACT READ WITH REGULATION 13(2)(H) OF THE CERC (SHARING OF INTER-STATE TRANSMISSION CHARGES AND LOSSES) REGULATIONS 2020 AND PURSUANT TO THE REPORT DATED 11.06.2026 OF THE COMMITTEE CONSTITUTED VIDE OFFICE ORDER DATED 30.07.2025 READ WITH ADDENDUM DATED 14.01.2026

A.	Executive Summary of the Petition

I.	Brief background of the Petitioners

1. 	Petitioner No. 1 - Serentica Renewables India 3 Private Limited (“Petitioner No. 1” / “SRI3PL”), a wholly owned subsidiary of Petitioner No. 2 - Serentica Renewables India Private Limited, is a generating company under Section 2(28) of the Electricity Act engaged in developing a 470 MW Hybrid (200 MW solar and 270 MW wind) power Project in Gadag, in the State of Karnataka (“Project”). The registered office of SRI3PL is at RMZ infinity, 5th Floor, Plot No. 15, Udyog Vihar, Phase IV, Gurugram, Haryana - 122015.

2. 	Petitioner No. 2 - Serentica Renewables India Private Limited (“Petitioner No. 2”/ “SRIPL”) is a company incorporated under the Companies Act 2013 and is the parent company of Petitioner No. 1 - SRI3PL. The registered office of SRIPL is at RMZ infinity, 5th Floor, Plot No. 15, Udyog Vihar, Phase IV, Gurugram, Haryana - 122015.

II.	Brief background of the Respondent

3. 	The Respondent - Central Transmission Utility of India Limited (“Respondent”/ “CTUIL”) is the Central Transmission Utility under Section 38 of the Electricity Act, undertaking the transmission of electricity through Inter-State Transmission System (“ISTS”) and discharging, inter alia, functions of planning and coordination relating to ISTS with all concerned authorities. The registered office of CTUIL is at “Saudamini”, Plot No-2, Sector-29, Gurgaon, Haryana - 122001.

III.	Brief Background of the matter

4. 	The Petitioners have filed the present Petition under Section 79(1)(c) of the Electricity Act 2003 read with Regulation 13(2)(h) and Regulation 27 of the CERC (Sharing of Inter-State Transmission Charges and Losses) Regulations 2020, as amended (“Sharing Regulations 2020”), seeking suitable directions and orders pursuant to findings in the Report dated 11.06.2026 issued by the Committee constituted vide Office Order dated 30.07.2025 read with Addendum dated 14.01.2026 (“Committee”) recommending extension of Scheduled Commercial Operation Date (“SCOD”) of its Project. In view of the various force majeure events which have adversely impacted the construction and commissioning of the Project as detailed in the Committee's Report and the present Petition, the Petitioners humbly request this Hon'ble Commission that 372 MW (146.87 MW Solar and 225.2 MW Wind) capacity of the Project, which stood commissioned as on 30.06.2026, is deemed to be commissioned as on 30.06.2025, thereby maintaining its eligibility for 100% waiver from payment of Inter-State Transmission System (“ISTS”) charges in terms of the relevant provisions of the Sharing Regulations 2020.

5.	Petitioner No. 1 - SRI3PL is developing a 470 MW Project for sale of power in terms of the following Power Delivery Agreements (“PDAs”):

(a)	PDA dated 31.03.2022 with Vedanta Limited (“VAL”) (amended on 22.09.2022) for supply of 180 MW RTC power (CUF - 55%),

(b)	PDA dated 17.02.2023 with Sterlite Copper (Captive) Limited (“Sterlite Copper”) for supply of 16 MW RTC power (CUF - 55%), and

(c)	PDA dated 17.02.2023 with Cairn India (Captive) Limited (“Cairn India”) dated 17.02.2023 for supply of 25 MW RTC power (CUF - 70%),

6.	In view of the timelines for commissioning of the Project, SRIPL (formerly Sterlite Power Technologies Private Limited) submitted the following applications to the Respondent - CTUIL seeking connectivity to the Inter-State Transmission System (“ISTS”) in terms of the CERC (Grant of Connectivity, Long Term Access and Medium-Term Open Access in Inter-State Transmission and related matters) Regulations 2009 (“Connectivity Regulations 2009”):

(a)	Stage I Connectivity Application No. 1200003738 dated 24.02.2022 for 400 MW connectivity at Gadag SS.

(b)	Stage II Connectivity Application No. 1200003761 dated 26.02.2022 (registered on 28.02.2022) for 165 MW connectivity at Gadag SS with the start date of connectivity as 01.07.2024.

(c)	Application No. 1200003828 dated 21.03.2022 (registered on 31.03.2022) for enhancement of Stage II Connectivity by 120 MW at Gadag SS.

7.	Subsequently, after notification of CERC (Connectivity and General Network Access to the inter-State Transmission System) Regulations 2022 (“GNA Regulations”), SRIPL submitted the following applications to CTUIL:

(a)	Application No. 2200000015 dated 17.04.2023 (re-applied on 29.04.2023) under Regulation 5.2 of the GNA Regulations seeking addition of generation capacity of 185 MW (without enhancement of connectivity) and change of fuel source from solar to hybrid (200 MW solar and 270 MW wind), with the start date indicated as 01.07.2024;

(b)	Applications dated 02.05.2023 for transition of connectivity from Connectivity Regulations 2009 to the GNA Regulations.

8.	SRIPL's applications were considered in the 21st and 22nd Consultation Meeting for Evolving Transmission Schemes in the Southern Region (“CMETS-SR”) held on 18.08.2023 and 25.08.2023, wherein SRIPL's applications for transition of connectivity and additional generation capacity were allowed.

9.	CTUIL granted in-principle approval of connectivity to SRIPL vide letters dated 09.10.2023 for 285 MW (100 MW + 80 MW + 65 MW + 40 MW) at Gadag PS wherein the start date for connectivity was 01.10.2024. The said start date of connectivity was confirmed vide the Final Grant of Connectivity dated 04.04.2024. Further, CTUIL also issued intimation dated 30.10.2023 approving SRIPL’s application for additional generation capacity of 185 MW. Accordingly, the total capacity of the Project was 470 MW (200 MW solar + 270 MW wind).

10.	Evidently, the SCOD of SRI3PL's Project and the start date of connectivity indicated in its Final Grant of Connectivity dated 04.04.2024 were before the cut-off date for 100% waiver of ISTS charges, i.e., 30.06.2025 (“ISTS waiver cut-off date”), thereby making SRI3PL eligible for the grant of 100% waiver of ISTS charges. However, despite SRI3PL's best efforts, commissioning of the Project has been delayed beyond the ISTS waiver cut-off date on account of the following uncontrollable / unforeseen factors and force majeure events:

(a) 	Delay in commissioning of the Common Transmission System (“CTS”) - In terms of the Final Grant of Connectivity, the start date of connectivity was 01.10.2024, and operationalization of connectivity for SRI3PL's Project required the commissioning of the CTS, including the Narendra New (GIS) - Pune (GIS) 765 kV D/C transmission line (“Narendra New line”) and the Gadag PS - Koppal PS 400 kV D/C line (“Gadag-Koppal line”). Pertinently, there is a substantial delay in commissioning of both these lines with the Gadag-Koppal line commissioned in March 2026 and the Narendra New line still anticipated to be commissioned by October 2026. As a result, SRI3PL was constrained to revise its timelines for execution of its Project in order to avoid mismatch in commissioning and stranding of its Project in the absence of requisite power evacuation facility, thereby delaying the SCOD of the Project.

(b)	Delay on account of transition of connectivity under the GNA Regulations and subsequent land acquisition challenges and unprecedented increase in price of land –

SRI3PL applied on 02.05.2023 for transition of its connectivity rights under the erstwhile Connectivity Regulations, 2009 to the GNA Regulations, 2022. However, the process remained pending for several months. In the 19th CMETS-SR meeting held on 29.05.2023, it was specifically recorded that SRI3PL application for addition of generation capacity would be considered only after completion of the GNA transition process. The transition was ultimately approved only in the 21st CMETS-SR meeting held on 18.08.2023, following which SRI3PL’S request for additional generation capacity was considered and approved in the 22nd CMETS-SR meeting held on 25.08.2023. Thereafter, CTUIL granted in-principle approval on 09.10.2023 and final approval only on 04.04.2024. Thus, there was a considerable delay in the transition of connectivity and associated approvals under the GNA framework, which was beyond Serentica's control.

During this period, the Project faced significant challenges in land acquisition, resulting in substantial cost escalation. There was an uncontrollable delay in acquisition of the required land due to fragmented land records at the tehsil offices, family disputes amongst landowners, and exorbitant compensation demands for critical pathway access. Owing to these circumstances and the prolonged development timeline, the land acquisition budget for the Project surged nearly fourfold, from approximately Rs. 30 crore to Rs. 118 crore. These factors collectively constituted circumstances beyond Serentica's reasonable control and materially impacted the implementation schedule of the Project.

(c)	Delay due to Right of Way (“RoW”) / Law and order issues including verbal threats to the workers at the project sites by the local landowners, difficulty in filing FIRs, etc., which hampered implementation of the Dedicated Transmission Line (“DTL”), Pooling Station and Project works from March 2024 till date (wind) and from April 2024 till date (solar).

(d)	Delay on account of extra-ordinary rainfall at the Project site during the months of May 2024 to September 2024 and May 2025 to September 2025, which severely hampered the project works.

(e)	Delay on account of event of force majeure being the collapse of towers at 5 locations of the 400 kV (Twin HTLS) Gadag ISTS – Narendra New Transmission line which impacted commissioning and trial runs for part capacity of 198 MW (Wind) and 162.5 MW (Solar), which had been installed and ready for commissioning as on 30.06.2025.

(f)	Administrative delay in CON-4 Approval - While SRIPL had applied for CON-4 approval for the hybrid capacity on 25.01.2024, the approval process was prolonged due to multiple iterations and technical queries from CTU/SRLDC.As a result, the Connectivity Agreement was executed only on 19.03.2025 thereby delaying trial run and commissioning timeline of the Project.

11.	Pursuant to this Hon’ble Commission's fourth amendment to the Sharing Regulations 2020 read with the Office Order dated 30.07.2025, SRI3PL filed an Application dated 12.03.2026 seeking recommendation of the Committee, for extension of 100% ISTS waiver in respect of the Project such that the Project is considered to be commissioned as on 30.06.2025. SRI3PL also made a presentation before the Committee on 22.04.2026 and submitted additional submissions including clarifications dated 26.04.2026.

12.	The Committee, vide its Report dated 11.06.2026, recognized that the delay in commissioning of the Project is attributable to transmission related reasons and Project related force majeure reasons, which are beyond SRI3PL's control and considered it appropriate to recommend:

(a)	Both permissible six-month extensions under Regulation 13(2)(h), i.e., extension up to 30.06.2026, or

(b)	till commissioning of the CTS associated with Gadag PS / actual COD of balance capacity,

whichever is earlier, for the purpose of maintaining eligibility of the Project for ISTS charges waiver. The findings and recommendations of the Committee are detailed in the subsequent paragraphs.

13.	Accordingly, the Petitioners have filed the present petition in furtherance of the Addendum dated 14.01.2026 to Office Order dated 30.07.2025 wherein the Renewable Energy Generating Stations (“REGS”) / Renewable Hybrid Generating Stations (“RHGS”) which have received recommendation of the Committee, such as SRI3PL, were required to approach this Hon'ble Commission for approval of extension of SCOD such that they are eligible for 100% waiver of ISTS charges.

IV.	Relief(s) sought in brief

14.	Please refer to Part VIII & IX of the present Petition.

B.	DETAILED PETITION

I.	Jurisdiction of the Hon'ble Commission

15.	It is submitted that in terms of Section 79(1)(c) of the Electricity Act, this Hon'ble Commission shall discharge the function of regulating inter-State transmission of electricity. The matter in issue in the present petition relates to extension of SCOD of the Project such that the Project is eligible for waiver of ISTS charges payable under the Sharing Regulations 2020, and therefore, falls within the jurisdiction of this Hon'ble Commission under Section 79(1)(c) of the Electricity Act.

16.	Further, under Regulation 13(2)(h)(ii) of the Sharing Regulations 2020 the aspect of extension of SCOD of REGS / RHGS which had SCOD before 30.06.2025 but could not commission within the said timelines on account of any Force Majeure event including non-availability of transmission system or for reasons not attributable to the REGS, was to be granted by this Hon'ble Commission based on the recommendation of the Committee.

17.	In terms of Explanation of Step 2 and 3 provided in the Addendum dated 14.01.2026 to the Office Order dated 30.07.2025, the RHGS which has received the recommendation of the Committee shall approach the Commission through a Miscellaneous Petition along with the report of the Committee and the relevant documents in support of their claim, and this Hon'ble Commission shall pass necessary order.

18.	In view of the above, the present Petition is being filed to place on record the Committee Report dated 11.06.2026 and seek extension of SCOD of the Project so as to become eligible for 100% ISTS waiver and becomes maintainable before this Hon'ble Commission.

II.	Details of the documents on which the petition is made

19.	The documents forming part of the Petition are mentioned in the List of Enclosures and annexed hereto.

III.	Limitation

20.	The cause of action in the present Petition is continuing in nature and arises from the delay in operationalization / availability of the CTS (Narendra New Line and Gadag-Koppal line). In so far as the Narendra New line has not been commissioned till date and is anticipated to be commissioned by October 2026 (in terms of the submission before the Committee), therefore, the delay in operationalization of CTS still persists thereby prejudicing SRI3PL's eligibility to a 100% waiver from ISTS charges. Accordingly, the present Petition is within limitation.

IV.	Facts of the case

A.	Connectivity Applications under Connectivity Regulations 2009 and PDAs

21.	On 24.02.2022, SRIPL (formerly Sterlite Power Technologies Private Limited) submitted Application No. 1200003738 to CTUIL for grant of Stage-I Connectivity for 400 MW in Gadag, Karnataka, under the Connectivity Regulations 2009. The connectivity was sought at Gadag SS. A copy of Stage-I Connectivity Application No. 1200003738 dated 24.02.2022 submitted by SRIPL to CTUIL is annexed hereto and marked as Annexure P [•].

22.	On 26.02.2022 (registered on 28.02.2022), SRIPL also submitted Stage-II Connectivity Application No. 1200003761 with CTUIL for 165 MW in Gadag SS, pursuant to the Stage-I Application. Such Stage II Connectivity was sought at Gadag SS with the start date of Connectivity as 01.07.2024. A copy of Stage-II Connectivity Application No. 1200003761 dated 26.02.2022 (registered on 28.02.2022) submitted by SRIPL to CTUIL is annexed hereto and marked as Annexure P [•].

23.	On 28.02.2022, SRI3PL wrote a letter to VAL indicating its willingness to supply 180 MW RTC power and invited VAL to proceed with execution of the relevant PDA. SRI3PL also informed VAL that supply of power to VAL is anticipated to commence from October 2024. A copy of the letter dated 28.02.2022 from SRI3PL to VAL is annexed hereto and marked as Annexure P [•].

24.	On 17.03.2022, Notice along with the Agenda for the 5th Consultation Meeting for Evolving Transmission Scheme (“CMETS”) in the Southern Region (“SR”) was issued by CTUIL wherein SRIPL's Connectivity Application No. 1200003738 for Stage-I connectivity of 400 MW and Application No. 1200003761 for Stage II connectivity for 165 MW at Gadag SS were listed for consideration.

25.	On 21.03.2022 (registered on 31.03.2022), seeking to enhance its connectivity allocation, SRIPL filed Application No. 1200003828 with CTUIL for enhancement of Stage II Connectivity by 120 MW at Gadag SS through the land and finance route. A copy of Application No. 1200003828 dated 21.03.2022 (registered on 31.03.2022) submitted by SRIPL to CTUIL is annexed hereto and marked as Annexure P [•].

26.	On 25.03.2022, the 5th CMETS-SR was held (Minutes dated 08.04.2022), wherein SRIPL was granted Stage I Connectivity for 400 MW and Stage II connectivity for 165 MW at Gadag SS with the start date of connectivity as 01.07.2024. The Transmission System identified for SRIPL was as under:

(a) Dedicated Transmission System for Connectivity:

- Through sharing of dedicated transmission line of M/s Vena Energy Vidyuth Pvt. Ltd i.e. Vena Energy Vidyuth Pvt. Ltd - Gadag PS 220kV S/c line strung on D/c tower.

(b) Common Transmission System for Connectivity (Under ISTS):

- Establishment of 1x500MVA, 400/220kV Gadag PS

- Gadag PS - Narendra (New) 400kV (high-capacity equivalent to quad moose) D/c line

- 1x125 MVAr, 420kV bus reactor at Gadag PS

Relevant extracts of the Minutes dated 08.04.2022 of the 5th CMETS-SR are annexed hereto and marked as Annexure P [•].

27.	On 31.03.2022, SRI3PL executed a PDA with VAL for supply of 180 MW Round-the-Clock (“RTC”) power at a Capacity Utilisation Factor (“CUF”) of 55%. The said PDA was amended on 22.09.2022. Copies of the PDA dated 31.03.2022 along with the Amendment Agreement dated 22.09.2022 are annexed hereto and marked as Annexure P [•].

28.	On 21.04.2022, Notice along with the Agenda for the 6th CMETS-SR was issued by CTUIL wherein SRIPL's Application No. 1200003828 for enhancement of Stage II Connectivity by 120 MW at Gadag SS was listed for consideration.

29.	On 29.04.2022, the 6th CMETS-SR was held (Minutes dated 18.05.2022), wherein SRIPL's application for enhancement of Stage II connectivity by 120 MW was allowed through the revised transmission system as under:

(a)	Dedicated Transmission System for Stage-II Connectivity:

- Pooling Station at switchyard of M/s Sterlite Power Technologies Pvt. Ltd at Gadag - Gadag PS 220kV S/c line including terminal bays at generation pooling station - under the scope of applicant

- 1 no. 220kV bay at Gadag PS end for termination of dedicated line under the scope of ISTS

(b)	Common Transmission System for Stage-II Connectivity - under ISTS:

- Establishment of 1x500MVA, 400/220kV Gadag PS

- Gadag PS - Narendra (New) 400kV D/c (high capacity equivalent to quad moose) line

- 1x125 MVAr, 420kV bus reactor at Gadag PS

Relevant extract of the Minutes dated 18.05.2022 of the 6th CMETS-SR are annexed hereto and marked as Annexure P [•].

30.	On 12.05.2022, SRI3PL sent a letter to VAL informing that the SCOD of its Project under the PDA is 30.06.2025, and SRI3PL would endeavour to commission and commence supply of power to VAL from 31.10.2024 on best efforts basis. A copy of SRI3PL's letter dated 12.05.2022 to VAL is annexed hereto and marked as Annexure P [•].

31.	On 07.06.2022, CTUIL granted Stage-II Connectivity for 285 MW (165 MW + 120 MW) to SRIPL at Gadag SS with the start date of connectivity as 01.07.2024. The Stage-II Grant of Connectivity Letter dated 07.06.2022 (along with revision dated 22.09.2022) by CTUIL is annexed hereto and marked as Annexure P [•].

32.	On 02.09.2022, SRI3PL wrote to Sterlite Copper, stating that it was willing to supply 16 MW RTC Power with a tentative start date of approximately 2 years from the execution of the PDA, and that it would commence supply of power tentatively from October 2024 onwards. A copy of SRI3PL's letter dated 02.09.2022 to Sterlite Copper is annexed hereto and marked as Annexure P [•].

33.	On 05.09.2022, SRI3PL wrote a letter to Cairn India indicating its willingness to supply 25 MW RTC power and invited Cairn India to proceed with execution of the relevant PDA. SRI3PL also informed that supply of power to Cairn India is anticipated to commence from October 2024. A copy of SRI3PL's letter dated 05.09.2022 to Cairn India is annexed hereto and marked as Annexure P [•].

34.	On 10.01.2023 (re-applied on 24.01.2023), SRIPL submitted LTA Application Nos. 0451100010 and 0451100011, for 100 MW and 80 MW, respectively. In terms of the LTA Applications, the start date for LTA was 01.10.2024. The LTA Application Nos. 0451100010 and 0451100011 dated 10.01.2023 are enclosed as Annexure P [•] (colly).

35.	On 17.02.2023. SRI3PL executed a PDA with Sterlite Copper for supply of 16 MW RTC power (CUF – 55%). A copy of the PDA dated 17.03.2023 between SRI3PL and Sterlite Copper is annexed hereto and marked as Annexure P [•].

36.	On 17.02.2023, SRI3PL executed a PDA with Cairn India for supply of 25 MW RTC power (CUF – 55%). A copy of the PDA dated 17.03.2023 between SRI3PL and Cairn India is annexed hereto and marked as Annexure P [•].

37.	On 14.03.2023, SRI3PL sent a letter to Sterlite Copper informing that the SCD of the Project is 30.06.2025 in terms of Article 1.1 of the PDA dated 17.02.2023, and SRI3PL would endeavour to commission and commence supply of power to Sterlite Copper from 31.10.2024 on best efforts basis. Letter dated 14.03.2023 from SRI3PL to Sterlite Copper is enclosed as Annexure P [•].

38.	On 14.03.2023, SRI3PL sent a letter to Cairn India informing that the SCD of the Project is 30.06.2025 in terms of Article 1.1 of the PDA dated 17.02.2023, and SRI3PL would endeavour to commission and commence supply of power to Cairn India from 31.10.2024 on best efforts basis. Letter dated 14.03.2023 from SRI3PL to Cairn India is enclosed as Annexure P [•].

B.	Capacity modification application and Transition under GNA Regulations 2022

39.	On 09.10.2022, this Hon'ble Commission notified the operationalization of certain provisions of the GNA Regulations 2022 w.e.f. 15.10.2022.

40.	On 01.04.2023, in partial modification of the Notification dated 14.10.2022, this Hon'ble Commission, inter alia, notified the effective date of Regulation 37.1 to Regulation 37.8 of the GNA Regulations as 05.04.2023, i.e. the Regulation under which entities can seek transition of connectivity from the Connectivity Regulations 2009 to the GNA Regulations 2022.

41.	The supply of power from SRI3PL to (i) VAL (180 MW RTC @ 55% CUF), (ii) Sterlite Copper (16 MW RTC @ 55% CUF), and (iii) Cairn India (25 MW RTC @ 70% CUF) was planned to be met from a combination of solar and wind power. Basis internal assessment by SRIPL, it was found that at the Gadag site, 55% CUF product could be provided by collocating wind along with solar at Gadag SS.

42.	On 17.04.2023 (re-applied on 29.04.2023), SRIPL submitted Application No. 2200000015 to CTUIL seeking addition of generation capacity of 185 MW (without enhancement of connectivity) under Regulation 5.2 of the GNA Regulations 2022, with the date from which such additional generation capacity would be added indicated as 01.07.2024.

43.	Along with the said Application, SRIPL also submitted a letter to CTUIL seeking change of fuel source of its Project from solar to hybrid (solar + wind) to ensure 55% CUF at the Gadag site. It is submitted that the application seeking fuel change was filed since:

(a)	SRI3PL was to supply power to VAL, Sterlite Copper and Cairn India on RTC basis at the rate of 55% / 70% CUF.

(b)	However, based on internal assessment of the Project site at Gadag, 55% CUF would be achieved by co-locating wind capacity along with solar capacity with the objective of maximum optimization.

(c)	Accordingly, SRIPL filed the fuel change application to convert the connectivity of 285 MW from 100% solar to hybrid (Solar - 200 MW + Wind - 270 MW).

A copy of Application No. 2200000015 dated 29.04.2023 submitted by SRIPL is annexed hereto and marked as Annexure P [•].

44.	On 02.05.2023, SRIPL filed the following Applications for transition of connectivity from Connectivity Regulations 2009 to the GNA Regulations:

(a)	Transition of Connectivity Application No. 1200003761 (115 MW) as per GNA Regulations 37.2 - 65 MW with connectivity start date as 01.10.2024

(b)	Transition of Connectivity application no. 1200003828 (120 MW) as per GNA Regulations 37.2 - 40 MW with connectivity start date as 01.10.2024

(c)	Transition of LTA application no. 0451100010 (100 MW) as per GNA Regulations 37.1 - 100 MW with connectivity start date as 01.10.2024

(d)	Transition of LTA application no. 0451100011 (80 MW) as per GNA Regulations 37.1 - 80 MW with connectivity start date as 01.10.2024

Copies of SRIPL's Applications dated 02.05.2023 for transition to GNA Regulations are annexed hereto and marked as Annexure P [•]. (Colly).

45.	Subsequently, in the 19th CMETS-SR meeting held on 29.05.2023, it was indicated that the said Application for addition of generation capacity shall be considered post completion of the GNA transition process.

46.	During the pendency of the Application for additional generation and change in fuel source, SRIPL had initiated the process for approval under Section 68 of the Electricity Act as under:

(a)	On 12.05.2023, SRIPL submitted an application to the CEA under Section 68 of the Electricity Act for installation of a Dedicated Transmission Line (Solar) from SRIPL’s Project’s switchyard to Gadag PS.

(b)	On 23.06.2023, CTUIL acknowledged SRIPL’s letter dated 29.04.2023 in respect of change in fuel source from solar to hybrid.

(c)	On 26.06.2023, CEA granted the approval under Section 68 for the DTL for the solar capacity.

(d)	On 01.07.2023, SRIPL submitted a revised application under Section 68 of the Electricity Act seeking a revision in the earlier approval dated 26.06.2023 to include hybrid lines (solar + wind).

(e)	On 17.07.2023, CEA provided its observations to SRIPL’s revised Section 68 application and advised SRIPL to approach CTUIL for revision in the allocated transmission system such that the revised application is in line with the CMETS-SR meetings.

SRIPL’s application dated 12.05.2023 and CEA’s approval dated 26.06.2023 are enclosed as Annexure [•] (colly).

47.	On 18.08.2023, the 21st CMETS-SR meeting was held (Minutes dated 14.09.2023) wherein SRIPL’s request for transition of connectivity for 285 MW (65 MW + 40 MW + 100 MW + 80 MW) under the Connectivity Regulations 2009 to connectivity under GNA Regulations was allowed with connectivity start date of 01.10.2024. Relevant extract of the Minutes dated 14.09.2023 of the 21st CMETS-SR is annexed hereto and marked as Annexure P [•].

48.	On 21.08.2023, Notice along with the Agenda for the 22nd CMETS-SR was issued by CTUIL wherein SRIPL 's Application for additional generation capacity of 185 MW as per the GNA Regulations 2022 (without enhancing the connectivity quantum of 285 MW) along with a change in configuration of the Dedicated Connectivity Line was listed for consideration.

49.	On 25.08.2023, the 22nd CMETS-SR meeting was held (Minutes dated 22.09.2023) wherein SRIPL’s application for additional generation capacity by 185 MW (under the GNA Regulations 2022) resulting in cumulative capacity of 470 MW along with change in configuration of dedicated transmission line from 220 kV S/c line to 220 kV S/c line on D/c tower was approved. Relevant extract of the Minutes dated 22.09.2023 of the 22nd CMETS-SR is annexed hereto and marked as Annexure P [•].

50.	On 09.10.2023, CTUIL sent four letters to SRIPL granting in-principle approval for 285 MW (100 + 80 + 65 + 40) MW capacity with the start date of connectivity as 01.10.2024 and SCD of the CTS as 16.07.2024. Copies of the in-principle grant of connectivity letters dated 09.10.2023 by CTUIL are annexed hereto and marked as Annexure P [•]. (Colly).

51.	On 30.10.2023, CTUIL sent an intimation of approval to SRIPL for additional generation capacity of 185 MW against Connectivity at Gadag PS and recognising the hybrid nature of SRIPL’s Project with a total installed capacity of 470 MW (200 MW solar + 270 MW wind). A copy of CTUIL's letter dated 30.10.2023 to SRIPL is annexed hereto and marked as Annexure P [•].

52.	On 13.11.2023, SRI3PL informed VAL, Sterlite Copper and Cairn India that CTUIL has granted in-principle approval for 285 MW capacity in SRI3PL's Project at Gadag PS with the date of operationalization of connectivity as 01.10.2024. Copies of letters dated 13.11.2023 from SRI3PL to VAL, Sterlite Copper and Cairn India are annexed hereto and marked as Annexure P [•] (Colly).

53.	On 16.11.2023, MoP granted the revised approval under Section 68 of the Electricity Act in respect of the hybrid (solar and wind) configuration of SRIPL's 470 MW hybrid Project as under:

(a) 220 kV S/c line on D/c towers from 270 MW wind project switchyard to SRIPL's Pooling Station;

(b) 220 kV S/c line on D/c towers from SRIPL's Pooling Station to Gadag PS.

A copy of the MoP's approval dated 16.11.2023 under Section 68 is annexed hereto and marked as Annexure P [•].

54.	On 19.02.2024, SRIPL sent a detailed breakup of the installed capacity to CTUIL.

55.	On 04.04.2024, CTUIL sent four separate letters to SRIPL granting final approval for 285 MW (100 + 80 + 65 + 40) MW capacity with the start date of connectivity as 01.10.2024 and the SCD of the Transmission System as 16.07.2024. In the final approval, the nature of SRIPL’s Project was correctly recorded as hybrid (solar + wind). In terms of the final approval for connectivity dated 04.04.2024 granted by CTUIL, the transmission system for SRIPL’s Project was as under:

(a)	Dedicated Connectivity Tr. System

(i)	Pooling Station at switchyard of M/s Serentica Renewable India Pvt. Ltd. at  Gadag PS 220kV S/c line including terminal bay at generation pooling station

(ii)	01 no. 220 kV bay at Gadag PS for termination of above dedicated line

(b)	Common Transmission system required for effectiveness of connectivity/GNA (System strengthening without ATS):

(i)	Transmission Scheme for Solar Energy Zone in Gadag (2500 MW), Karnataka – Part-A:

Phase-I:

- 2x500 MVA, 400/220 kV Gadag PS along with 1X125 MVAr, 400kV bus reactors

- Gadag PS – Narendra (New) 400 kV D/c line

Phase-II:

Gadag PS – Koppal PS 400 kV D/c line

400/220 kV, 3x500 MVA ICT Augmentation at Gadag PS

(ii)	ISTS Network Expansion scheme in Western Region & Southern Region for export of surplus power during high RE scenario in Southern Region

- Narendra New (GIS) – Pune (GIS) 765kV D/c line with 1x330mVAr switchable line reactor on each ckt at both ends

- Upgradation of Narendra (New) (GIS) to its rated voltage of 765 kV level along with 4x1500 MVA transformer and 2x330 MVAr Bus Reactor

The four letters issued by CTUIL granting the final approval to SRIPL are enclosed as Annexure P [•] (Colly.).

56.	On 08.05.2024, SRI3PL informed VAL, Sterlite Copper and Cairn India that CTUIL has granted final approval for 285 MW capacity in SRI3PL's Project at Gadag PS with the date of operationalisation of connectivity as 01.10.2024. Copies of letters dated 08.05.2024 from SRI3PL to VAL, Sterlite Copper and Cairn India are annexed hereto and marked as Annexure P [•] (Colly).

57.	On 30.05.2024, MoP issued a letter providing that all Renewable Energy projects that had applied for connectivity up to 30.06.2023 and whose commissioning dates may go beyond 30.06.2025 due to delay in transmission system should be considered for 100% waiver from ISTS charges of they commission their projects as per the date of commissioning of the associated ISTS or scheduled date of commissioning as mentioned in the connectivity application, whichever is later. Minutes of Meeting of this Hon’ble Commission held on 31.05.2024 recording the contents of the MoP letter dated 30.05.2024 is enclosed as Annexure P [•].

58.	On 20.07.2025 and 07.08.2025, SRIPL submitted four Applications to CTUIL seeking addition of generation capacity of 107 MW (without enhancement of connectivity) under Regulation 5.2 of the GNA Regulations 2022, as follows:

(a)	Application No. 2200002270 for addition of 30 MW (10.4 MW solar, 16.8 MW wind and 2.8 MW BESS)

(b)	Application No. 2200002271 for addition of 24.4 MW (8.4 MW solar, 13.7 MW wind and 2.3 MW BESS)

(c)	Application No. 2200002272 for addition of 15.1 MW (5.2 MW solar, 8.5 MW wind and 1.4 MW BESS)

(d)	Application No. 2200002273 for addition of 37.5 MW (13 MW solar, 21 MW wind and 3.5 MW BESS)

The date from which such additional generation capacity would be added was indicated as 31.12.2027. Copies of Applications dated 20.07.2025 and 07.08.2025 for additional generation capacity are enclosed as Annexure P [•] (colly.).

59.	On 20.08.2025, the 40th CMETS-SR was held (Minutes dated 08.10.2025) wherein SRIPL’s applications for addition of generation capacity of 107 MW was allowed with the start date of addition of such additional generation capacity as 31.12.2027. Relevant extract from the 40th CMETS-SR held on 20.08.2025 is enclosed as Annexure P [•].

60.	On 05.12.2025, CTUIL sent intimations of approval to SRIPL for additional generation capacity of 107 MW against Connectivity at Gadag PS. CTUIL’s intimation dated 05.12.2025 for additional generation capacity of 107 MW is enclosed as Annexure P [•] (colly.).

61.	On 24.12.2024, CTUIL issued a Corrigendum to the Final approval of Connectivity dated 04.04.2024 with respect to 80 MW capacity to SRIPL, revising the installed capacity of the Project as 132 MW (56 MW solar and 76 MW wind) instead of 165 MW that was inadvertently recorded in the Approval dated 04.04.2024. Pertinently, the start date of connectivity as 01.10.2024 and the Scheduled Date of Commissioning of the Transmission System as 16.07.2024 were not revised. A copy of the Corrigendum dated 24.12.2024 issued by CTUIL is annexed hereto and marked as Annexure P [•].

C.	Force Majeure Notices issued by SRI3PL

62.	On 23.05.2025, SRI3PL wrote to VAL issuing a force majeure notice notifying the occurrence of uncontrollable events, including unprecedented rainfall delaying project works, RoW issues like agitation by farmers and political intervention hindering project works, and land conversion issues. Coupled with the delay in completion of the CTS, i.e. the Narendra New 765 kV line and the Gadag-Koppal line, the Project is likely to be commissioned by May 2026. A copy of SRI3PL's letter dated 23.05.2025 is annexed hereto and marked as Annexure P [•].

63.	On 13.05.2025, five towers at Location Nos. 16/4, 16/6, 16/7, 16/8 of the 400 kV D/C (Twin HTLS) Gadag ISTS - Narendra New Transmission Line collapsed due to inclement weather conditions. On 23.05.2025, SRI3PL issued force majeure notices to its beneficiaries under Article 11 of the respective PDAs notifying them about the said force majeure event. The towers were restored only on 28.06.2025. Copies of SRI3PL's force majeure notices dated 23.05.2025 are annexed hereto and marked as Annexure P [•].

64.	On 03.07.2025 and 14.10.2025, SRI3PL wrote to VAL, Sterlite Copper and Cairn India issuing notices of the delay impacting the Project on account of unprecedented rainfall and RoW issues which hampered project works. Copies of the letters dated 03.07.2025 and 14.10.2025 are annexed hereto and marked as Annexure P [•].

65.	On 12.03.2026, SRI3PL submitted its Application before the Committee seeking recommendation for extension of 100% waiver of ISTS charges in terms of Section 13(2)(h) of the Sharing Regulations 2020 such that the Project is deemed to be commissioned as on 30.06.2025. SRI3PL also submitted an additional submission dated 20.03.2026 and made a presentation before the Committee on 22.04.2026, followed by additional submissions including clarifications dated 26.04.2026. Copies of the Application dated 12.03.2026 and additional submissions dated 20.03.2026 and 26.04.2026 (without annexures) are annexed hereto and marked as Annexure P [•].

66.	On 11.06.2026, the Committee issued its Report observing as under:

(a)	The following events were beyond the reasonable control of the Petitioners and have materially impacted the commissioning schedule [Para 8] –

A.	Transmission Related

(i)	delay in commissioning of Narendra New Line and Gadag-Koppal line

(ii)	Unavailability of Gadag PS Section -II

(iii)	Low visibility of evacuation system readiness

(iv)	Delay due to GNA transition

B.	Project related Force Majeure

(i)	Land acquisition due to high compensation

(ii)	Law and order issues

(iii)	Adverse weather conditions

(iv)	Delay in statutory approvals

(b)	The original SCOD of the Project (30.06.2025) satisfies the eligibility requirement under Regulation 13(2)(h) [Para 9.1], and Connectivity was sought well in advance and final grant of connectivity was also obtained before SCOD [Para 9.2].

(c)	Major delay in commissioning of the Project occurred because the CTS required for effective evacuation, particularly the Narendra New line, has been substantially delayed and is now expected only by October 2026 [Para 9.3].

(d)	The project-side infrastructure including DTL and PSS is substantially ready, and large capacity has already been commissioned [Para 9.4].

(e)	The delay in SCOD of the Project is therefore primarily attributable to transmission system delay and other force majeure events, and not due to lack of readiness on the part of the developer [Para 9.5].

67.	In view of the above, the Committee recommended grant of both permissible six-month extensions (a total extension of 12 months) of SCOD of the Project, i.e., up to 30.06.2026 or till commissioning of the CTS associated with Gadag PS / actual COD of balance capacity, whichever is earlier. Relevant extract from the Report dated 11.06.2026 is as under:

“10.1 In terms of Regulation 13(2)(h), extension of SCOD is to be granted in blocks of six months at a time, subject to a maximum of two such extensions.

10.2 Since the original SCOD is 30.06.2025, the first extension goes up to 31.12.2025 and the second permissible extension falls up to 30.06.2026.

10.3 As on date, even the first six-month period has already elapsed without availability of the critical transmission system and without full commissioning of the Project.

10.4 Therefore, to avoid multiplicity of proceedings and repeated applications, the Committee considers it appropriate to recommend both the permissible six-month extensions at this stage.

10.5 Accordingly, the Committee recommends extension of SCOD of the 470 MW Gadag Phase-I Hybrid Project:

- First Extension: up to 31.12.2025

- Second Extension: up to 30.06.2026

or till commissioning of the Common Transmission System / actual COD of balance capacity, whichever is earlier, for the limited purpose of maintaining eligibility for waiver of ISTS transmission charges.”

A copy of the Committee Report dated 11.06.2026 is annexed hereto and marked as Annexure P [•].

D. 	Current status of the Project

68.	Based on the current status of Project works, SRI3PL has commissioned 372 MW by June 2026 as under:

(a)	Solar capacity of 146.8 MW commissioned as on 30.06.2026

(b)	Wind capacity of 225.2 MW commissioned as on 30.06.2026.

Copies of the Trial Run Certificates and the COD Intimation letters for the commissioned capacity are annexed hereto and marked as Annexure P [•] (Colly).

[Trilegal Note – Please provide the details re. commissioning and the Trial Run and COD Intimation letters.]

69.	Evidently, and as recognized by the Committee vide its Report dated 11.06.2026, SRI3PL has achieved substantial progress in project works which evinces SRI3PL's bona fides and efforts to mitigate the delays caused by events beyond its control.

70.	A brief summary of project milestones and status is provided below:

| Milestone | Solar | Wind |
| --- | --- | --- |
| Construction Plan |  |  |
| Prelim Works - topography, soil testing, excavation | June 2023 to March 2026 | March 2023 to April 2025 |
| Engineering - SLD, drawings, equipment etc. | February 2023 to February 2026 | July 2023 to April 2025 |
| Procurement |  |  |
| Ordering - Module, Inverter, WTG, EPC contracts | January 2023 to September 2023 | November 2022 to December 2022 |
| Supply of Ordered Equipment | January 2023 to May 2025 | October 2023 to December 2025 |
| Land | April 2023 to January 2026 (87% acquired; balance 13% by March 2026) | March 2023 to April 2025 (100% acquired - 443 acres) |
| Construction |  |  |
| Plant Side | 162.5 MW installed as on 30.06.2025; remaining by April 2026 | 198 MW installed as on 30.06.2025; remaining by April 2026 |
| PSS & DTL | PSS and DTL complete by November 2024 | PSS and DTL complete by January 2025 |
| CEA / CEIG Inspection | PSS (31.03.2024), DTL (30.05.2024), 100 MW (30.11.2024), 162.5 MW (10.06.2025), 200 MW (07.01.2026) | PSS (30.03.2024), DTL (30.06.2024), 25 WTGs (11.04.2024), 14 WTGs (31.03.2025), 10 WTGs (06.06.2025), 31 WTGs (20.06.2025), 15 WTGs (29.12.2025) |
| Commissioning |  |  |
| Commissioned as on date | 146.86 MW Solar | 225.2 MW Wind |

[Trilegal Note – Request Serentica to update the table basis the current status of the Project.]

V. 	Facts in issue and Questions of Law

71.	The facts in issue are set out in Paragraphs [•] above.

72.	The questions of law that arise for consideration by this Hon'ble Commission are as under:

(a) 	Whether SRI3PL is entitled to extension under Regulation 13(2)(h) of the Sharing Regulations 2020 for the purpose of maintaining eligibility for waiver of ISTS charges, when delay in commissioning of the Project has arisen primarily due to non-availability / delay in the CTS (including the Narendra New line and the Gadag-Koppal line), along with other force majeure events including collapse of five towers of the 400 kV D/C Gadag ISTS - Narendra New Transmission Line, administrative delay in CON-4 approval, delay in land acquisition, delay due to unprecedented rainfall, and delay due to RoW and law and order challenges - all of which were beyond SRI3PL's control?

(b)	Whether the delay in operationalisation of connectivity and associated transmission system, and delay in grant of statutory approval necessary for evacuation of power, qualify as circumstances warranting relief under Regulation 13(2)(h) of the Sharing Regulations 2020?

(c) 	Whether, in view of the Addendum dated 14.01.2026 and the Recommendation Report dated 11.06.2026 of the Committee constituted by this Hon'ble Commission, SRI3PL is entitled to an order from this Hon'ble Commission granting approval towards extension in SCOD of the entire 470 MW capacity of its Project till 30.06.2026, thereby maintaining eligibility for corresponding waiver from payment of 100% ISTS charges till such date?

VI.	Submissions

73.	At the outset, SRI3PL submits that the present Petition is maintainable and deserving of relief under Regulation 13(2)(h) of the Sharing Regulations. The Project was conceived, contracted and pursued on the basis of a commissioning schedule aligned with 30.06.2025. The subsequent delays arose due to connectivity and transmission related and statutory approval-related events beyond SRI3PL's control. SRI3PL's claim therefore falls squarely within the category of cases for which the Office Order dated 30.07.2025 (read with the Addendum dated 14.01.2026) contemplates extension.

A.	Development of the Project was premised on the SCOD being 30.06.2025

74.	It is submitted that even prior to execution of the PDAs, SRI3PL, vide letters dated 28.02.2022, 02.09.2022 and 05.09.2022, communicated to VAL, Sterlite Copper and Cairn India that it is anticipating commencement of supply of power to VAL by October 2024, on a best effort basis.

75.	Consistent with the above, SRIPL applied for connectivity in February / March 2022 and April / May 2023 and sought connectivity date of 01.07.2024 accordingly. The Petitioners, therefore, acted sufficiently in advance and structured the Project on a timeline intended to ensure commissioning by October 2024, on a best effort basis.

76.	The PDAs dated 31.03.2022 (as amended), 17.02.2023 (with Sterlite Copper) and 17.02.2023 (with Cairn India) also record the Project's contractual commissioning schedule wherein SCOD of the Project has been stated as 30.06.2025 with commencement of supply of power by October 2024, on a best effort basis. The same is also evident from SRI3PL's letters dated 12.05.2022 to VAL, 14.03.2023 to Sterlite Copper and 14.03.2023 to Cairn India.

77.	It is submitted that in terms of the applications dated 02.05.2023 submitted by SRIPL for transition of connectivity to GNA Regulations, SRIPL had sought connectivity start date of 01.10.2024. Further, SRIPL's application dated 29.04.2023 under Regulation 5.2 of the GNA Regulations also mentions that the said capacity shall be added by 01.07.2024. Even the in-principle approvals for connectivity dated 09.10.2023 and the final grant of connectivity dated 04.04.2024 issued by CTUIL provided the same connectivity start date of 01.10.2024. Pertinently, these actions demonstrate diligence and proactive mitigation, not delay attributable to SRI3PL.

78.	Pertinently, vide its Report dated 11.06.2026, the Committee has also observed that the SCOD of the Project was 30.06.2025, as mentioned in the PDAs and the letters sent to the consumers - VAL, Sterlite Copper and Cairn India [Para 3.1]. Therefore, the construction and commissioning activities at the Project were aligned with such timelines. However, SRI3PL could not commission its Project on the SCOD on account of reasons entirely beyond SRI3PL's control, as detailed below.

B.	Delay in operationalization of connectivity due to delay in commissioning of CTS

79.	It is submitted that the Narendra New line and the Gadag-Koppal line (both developed under TBCB route) are parts of the CTS required to evacuate power from the Project.

80.	Notably, at the time of in-principle grant of connectivity dated 09.10.2023, the anticipated SCD of the Gadag-Koppal line and the Narendra New  line was May 2024 and July 2024, respectively, as evident from the CEA MPR for October 2023. At that juncture, there was no indication that the commissioning of the Gadag-Koppal Line and the Narendra New Line and operationalization of connectivity would be delayed.

81.	However, at the time of final grant dated 04.04.2024, commissioning of the CTS was delayed to December 2024 as evident by the CEA MPR for April 2024. Even in such scenario, the CTS would have been commissioned prior to the ISTS waiver cut-off date, i.e., 30.06.2025. Relevant extract from the MPR issued by CEA for October 2023 and April 2024 are enclosed as Annexure [•] (colly).

82.	It is submitted that even after issuance of the final grant of connectivity dated 04.04.2024, there has been delay in the commissioning of the CTS, detailed as under:

(a)	Narendra New line

83.	Basis the recommendations of the 8th meeting of the National Committee on Transmission (“NCT”) held on 25.03.2022 (Minutes dated 05.05.2022), the Narendra New line was to be implemented through TBCB route within 18 months from the date of transfer of the SPV. While the Request for Proposal (“RFP”) for the Narendra New line was issued in July 2022, the SPV was transferred only on 17.01.2023. Accordingly, the original SCD of the Narendra New line was July 2024, i.e. 18 months from 17.01.2023, as tabulated hereunder:

| Sr. No. | Particulars | Date |
| --- | --- | --- |
| 1. | Request for Proposal issued by the Bid Process Co-ordinator - REC Power Development and Consultancy Limited | 25.07.2022 |
| 2. | Issuance of Letter of Intent | 26.12.2022 |
| 3. | Acquisition of SPV - WRSR Power Transmission Limited (A subsidiary of Adani Transmission Limited) | 17.01.2023 |
| 4. | Execution of Transmission Service Agreement (TSA) | 17.01.2023 |
| 5. | Grant of Transmission Licence by Hon’ble CERC | 17.04.2023 |
| 6. | Tariff adoption by this Hon’ble Commission | 26.03.2023 |
| 7. | Scheduled Date of Completion (18 months from transfer of SPV) | 16.07.2024 |

84.	In addition to the pre-implementation delay in the Narendra New  line on account of delay in transfer of the SPV, the timeline for the anticipated SCD of the line has continuously been delayed. As on date the anticipated SCD of the Narendra New 765 kV line in terms of the MPR for July 2026 issued by CEA is October 2026. The delay in commissioning of the Narendra New 765 kV line in terms of the MPR is tabulated as under:

| Sl no. | MPR issued by CEA (months) | Anticipated SCD |
| --- | --- | --- |
| 1. | January 2024 | October 2024 |
| 2. | June 2024 | December 2024 |
| 3. | October 2024 | March 2025 |
| 4. | January 2025 | May 2025 |
| 5. | June 2025 | September 2025 |
| 6. | August 2025 | December 2025 |
| 7. | September 2025 | March 2026 |
| 8. | December 2025 | June 2026 |
| 9. | January 2026 | June 2026 |
| 10. | July 2026 | October 2026 |

The construction status of Narendra New line as per CEA July 2026 report is as below:

| S. N | Particulars | Status |
| --- | --- | --- |
| Total Locations are: 795 Nos |  |  |
| 1 | Foundation completed (Nos) | 795 |
| 2 | Erection competed (Nos) | 726 |
| 3 | Stringing completed (Ckm) | 294 |
| 4 | ROW issues (Loc.) | 51 |
| 5 | Revised SCOD | October 2026 (This is the 8th revision from the Original SCOD -16.07.2024 |

Relevant extract from the MPR issued by the CEA for July 2026 is enclosed as Annexure [•].

(b)	Gadag – Koppal line

85.	Similarly, in terms of the 8th NCT held on 25.03.2022, the Gadag – Koppal line was to be implemented through the TBCB route within 18 months from the date of transfer of the SPV. While the RFP for the Gadag – Koppal line was issued in February 2022, the SPV was transferred only on 18.11.2022. Accordingly, the originnal SCD of the Gadag - Koppal line was May 2024.

86.	However, the line was commissioned only by March 2026 since in addition to the pre-implementation delay in the Gadag - Koppal line, the timeline for the anticipated SCD of the line was continuously delayed, and the line was commissioned only in March 2026.

87.	Therefore, there has been a substantial delay in commissioning of the CTS. While the Gadag-Koppal line was finally commissioned in March 2026, the Narendra New 765 kV line is yet to be commissioned. As stated above, in terms of MPR for July 2026, the Narendra New line is anticipated to achieve SCD only by October 2026, thereby shifting the start date of connectivity beyond 30.06.2025 (the stipulated cut-off date for commissioning of SRI3PL’s Project in order to be eligible for the waiver from ISTS charges).

88.	Notably, SRI3PL issued (a) letter dated 16.06.2025 to Sterlite Copper and (b) letter dated 04.02.2026 to Cairn India notifying them of the delay in commissioning of SRI3PL’s Project on account of the delay in commissioning of the CTS (i.e. the Narendra New line). SRI3PL’s letters dated 16.06.2025 and 04.02.2026 are enclosed as Annexure [•] (colly.).

Re.	Delay in grant of temporary transmission evacuation to SRIPL and performance of FTC / trial run

89.	Due to delay in commissioning of the CTS, SRIPL was constrained to apply for T-GNA to ensure that the commissioned capacity is not left stranded. Pertinently, the evacuation granted to SRIPL at Gadag SS was in Section II, which was not ready for evacuation in June 2025, in spite of the scheduled timeline for its readiness being in October 2024. Therefore, evacuation had to be temporarily facilitated through Gadag SS Section I.

90.	On 19.02.2025, a meeting was held (Minutes dated 28.03.2025) with participants from Renew Transmission Ventures Pvt Ltd, CTUIL and SRIPL, wherein CTUIL clarified that pending commissioning of the CTS provided in the final grant dated 04.02.2024, SRIPL may schedule power under T-GNA.  It took approximately 90 days (from January 2025 to March 2025) for SRIPL to obtain necessary approvals from CTUIL and Renew Transmission Ventures Pvt Ltd for evacuating power through Section I. Due to the delay in transmission evacuation, SRIPL could not perform FTC/Trial-run in the originally granted Section II of Gadag SS. Minutes of the meeting dated 28.03.2025 is enclosed as Annexure P [•].

91.	In spite of the above arrangement, there was uncertainty on exact quantum of evacuation as well as possibility of curtailment of power due to non-availability of network when other developers commence generation or any other reasons not attributable to SRIPL. Notably (i) T-GNA evacuation has lowest priority, (ii) evacuation using T-GNA due to delay in commissioning of transmission network was beyond SRIPL’s control and (iii) curtailment under T-GNA is not treated as force majeure. Therefore, curtailment under T-GNA may result in generation losses and levy of liquidated damages under the PDAs. For instance, Renewable Energy Projects located in Rajasthan are currently stranded and are unable to evacuate approximately 100% of the power generated since December 2025, due to commissioning of the Khetri-Narela Line which led to reduction of available margins for T-GNA.

92.	In any event, SRI3PL has commissioned 372 MW capacity of the Project by June 2026, and therefore, is eligible for 100% waiver of ISTS charges.

93.	The delay in achieving SCOD on account of the delay in readiness of the CTS and consequent operationalisation of connectivity for the Project has also been recognized by the Committee. Vide its Report dated 11.06.2026, the Committee has specifically observed that [Para 9]:

(a)	The major delay occurred because the CTS required for effective evacuation, particularly the Narendra New - Pune 765 kV D/C Line, has been substantially delayed and is now expected only by October 2026.

(b)	The project-side infrastructure including DTL and PSS was substantially ready, and large capacity has already been commissioned.

(c)	The delay in SCOD of the Project is therefore primarily attributable to transmission system delay and other force majeure events, and not due to lack of readiness on the part of the developer.

94.	In consideration of the above, the Committee granted extension of SCOD of the Project up to 30.06.2026 (two extensions of 6 months in terms of Regulation 13(2)(h)), or till commissioning of the CTS associated with the Gadag PS / actual COD of balance capacity, whichever is earlier.

C.	Delay in land acquisition and challenge of cost escalation

95,	As stated above, all power projects plan their activities so as to synchronize the SCOD of the Project with the start date of connectivity in order to avoid any stranded capacity.

96.	SRI3PL faced significant delay in land acquisition due to the following reasons which were beyond its control:-

C1.	Uncertainty and delay due to transition into GNA Regime

(a)	Post notification of Regulation 37 of the GNA Regulations 2022, there was uncertainty regarding the timelines for operationalization of connectivity with respect to the Project. As a result, SRI3PL did not have visibility as to the date on which connectivity would be operationalized including the commissioning of the CTS including Narendra New line and the Gadag – Koppal line. Consequently, there was uncertainty as to the point of evacuation for the power generated from the Project which resulted in the land acquisition activities being delayed.

C2.	Unprecedented increase in price of contiguous land

(b)	Commissioning of the Project has also been delayed on account of an unprecedented increase in the price of contiguous land resulting in a sharp increase in the initial budgeted cost of Rs. 30 crores towards land to an estimated cost of Rs. 118 crores (almost four times the budgeted cost) along with significant RoW issues such as verbal threats to workers at the project sites by the local landowners, difficulty in filing FIRs, etc. Such delay in land acquisition was for reasons not attributable to SRI3PL.

97.	Land acquisition for solar and wind projects has been adversely impacted due to difficulties in acquiring pathway land required to access the WTGs, family disputes of landowners, incomplete land records in tehsil office, exorbitant prices demanded by the landowners, etc.

98.	It is a prudent utility practice that developers plan project timelines in a manner to align SCOD of the Project with the start date / operationalization of the connectivity in order to avoid capacity being stranded in the absence of requisite evacuation facilities. Therefore, uncertainty due to transition into the GNA regime and unprecedented increase in price of contiguous land led to delay in the timelines for achieving different Project Milestones (including land acquisition). This delay is for reasons beyond SRI3PL's control and falls within the scope of Regulation 13(2)(h) of the Sharing Regulations.

D.	Delay in completion of project works on account of severe RoW issues

99.	Despite timely action by SRI3PL, there has been a delay in completion of construction works in the Project due to severe RoW issues and heavy rainfall which adversely impacted the Project timelines.

100.	SRI3PL faced significant RoW and Law & Order issues on account of verbal threats from the local population, denial of access due to farmer/local agitation, lack of guidelines for compensation qua the 33 kV line, obstructions created by locals (including obstacles which adversely impacted vehicular movement) and before courts.

101.	With respect to the wind component, SRI3PL faced a cumulative delay from March 2024 till date on account of RoW issues pertaining to civil and mechanical works for the wind component of the Project and the foundation, erection and stringing works relating to the 33kV line. In spite of the 'Guidelines for payment of compensation in regard to RoW for transmission line' notified by the MoP on 14.06.2024, the locals have been demanding exorbitant amounts towards RoW compensation for laying down dedicated transmission lines. Further, denial of access to WTG locations by the farmers and repeated obstruction to the access roads by the landowners have delayed movement of material and equipment to the WTG locations thereby resulting in stoppage of project works (including civil and mechanical) at the WTG locations and disruption of project timelines.

102.	With respect to the solar component, SRI3PL faced a cumulative delay from April 2024 till date on account of RoW issues created by the locals at the Solar Project site, such as denial of access to the project site to the Engineers and EPC contractors by the farmers, and deliberate obstructions created by landowners - digging trenches, placing barricades, blocking roads with vehicles, etc., which prevented movement of material and personnel.

103.	In this regard, SRI3PL wrote multiple letters from March 2024 to February 2026 to the District Collector, Gadag seeking urgent intervention for resolution of the above-mentioned law and order issues at various locations. Copies of SRI3PL's letters to the DC, Gadag are annexed hereto and marked as Annexure P [•] (Colly.) (wind component) and Annexure P [•] (Colly.) (solar component).

E.	Delay due to heavy rainfall

104.	It is submitted that from May 2024 to September 2024 and then May 2025 to September 2025, there was an unprecedented amount of rainfall which rendered the pathways to the site inaccessible and further delayed construction activities as the rain made the soil soggy and unfit for heavy machinery movement. The unprecedented rainfall in May 2024 to September 2024 had adversely impacted the development works at the WTG locations. Further, the unprecedented rains during May 2025 to September 2025 impacted the WTGs readiness for undergoing trial runs which require SCADA communication, metering checks, time drift report, protection relay mapping as per signal list, signature test for equipment etc.

105.	The factum of excess rainfall in Gadag and surrounding districts is supported from the data provided by Karnataka State Natural Disaster Monitoring Centre (“KSNDMC”). This is corroborated by data provided by Water Resource Department, Government of Karnataka. Copy of the data provided by KSNDMC is annexed hereto and marked as Annexure P [•].

106.	As a result of such unprecedented and heavy rainfall, the soil at the WTG locations became very soft due to significant absorption of water. Consequently, water logging has been caused at WTG sites and adversely impacted the Project works in spite of measures taken by SRI3PL to mitigate the impact of seasonal rainfall.

F.	Delay in commissioning of installed capacity of 360.5 MW for reasons beyond the control of SRI3PL

107.	It is submitted that in spite of the above-mentioned events, SRI3PL acquired the requisite land and successfully installed a total of 360.5 MW capacity with the available land as on 30.06.2025, i.e., (i) Solar - 162.5 MW out of 200 MW; and (ii) Wind - 198 MW out of 270 MW, as detailed hereunder:

(a)	Wind component (198 MW out of 270 MW): Wind PSS and 25 WTGs were mechanically ready and installed as on 30.03.2024 and Wind PSS to Solar PSS DTL was ready as on 30.06.2024. Further, 55 WTGs (198 MW) were ready as on 30.06.2025.

(b)	Solar component (162.5 MW out of 200 MW): Solar PSS was ready as on 31.03.2024 and DTL from Solar PSS to ISTS substation was ready as on 30.05.2024 and 100 MW Solar capacity was installed as on 30.11.2024. However, trial run for the said capacity could not be undertaken due to the absence of Connectivity Agreement (which was executed on 19.03.2025) as Con 4 was under evaluation. As on 30.06.2025, 162.5 MW solar out of total of 200 MW was installed.

Therefore, with the requisite evacuation facilities, SRI3PL would have been able to commission part capacity of the Project on 23.05.2025, i.e., before the ISTS waiver cut-off date of 30.06.2025.

108.	As on date of filing of the application for extension of SCOD before the Committee on 12.03.2026, the following capacity was ready for commissioning as is evident from the following CEIG Safety approvals issued to SRI3PL:

(a)	Solar component - PSS (31.03.2024), DTL (30.05.2024), 100 MW (30.11.2024), 162.5 MW including previous 100 MW (10.06.2025) and the total 200 MW (07.01.2026)

(b)	Wind component - PSS (30.03.2024), DTL (30.06.2024), Wind Capacity: 25 WTGs (11.04.2024), 14 WTGs (31.03.2025), 10 WTGs (06.06.2025), 31WTGs including previous 25 WTGs (20.06.2025), 15 WTGs including pervious 10 WTGs (29.12.2025

The CEIG Safety approvals dated 31.03.2024, 30.05.2024, 30.11.2024, 10.06.2025, 07.01.2026 for the solar component and CEIG Safety approvals dated 30.03.2024, 30.06.2024, 11.04.2024, 31.03.2025, 06.06.2025, 20.06.2025 and 29.12.2025 for wind component are enclosed as Annexure P [•]. (Colly.).

109.	However, in spite of the same, the Project could not be commissioned on account of administrative delay in Con-4 approval and the force majeure event of tower collapse at 5 locations and detailed below:

D1.	Administrative Delay in CON-4 Approval

110.	On 25.01.2024, SRI3PL applied for CON-4 approval for the hybrid capacity of 285 MW connectivity for its 470 MW Project. However, the approval process was prolonged due to multiple iterations and technical queries from CTU/SRLDC. Copy of SRI3PL’s application dated 25.01.2024 is enclosed as Annexure P [•].

111.	Consequently, the Connectivity Agreement was only executed on 19.03.2025 Since trail runs could not have commenced without a valid Connectivity Agreement, the above-mentioned administrative delay resulting in delaying the commissioning timeline. Copy of the Connectivity Agreement dated 19.03.2025 is enclosed as Annexure P [•].

D2.	Delay due to force majeure event of collapse of towers at 5 locations

112.	Even after the successful installation of 360.5 MW capacity, such capacity could not be commissioned on account collapse of 400KV D/C (Twin HTLS) Gadag ISTS -Narendra New Transmission line tower connecting Gadag ISTS S/s to Narendra (New) S/s at 5 locations due to inclement weather conditions which qualify as a Force Majeure Event. The relevant details regarding the force majeure event and the delay caused on account of the same is detailed below:

(a)	The Project is connected to the 400KV D/C (Twin HTLS) Gadag ISTS-Narendra New Transmission line. On 13.05.2025, five towers at Location Nos. 16/4,16/6,16/7,16/8 of the said line collapsed due to inclement weather conditions. The same is evident from the report of the Southern Region Load Despatch Centre dated 19.05.2025 which is enclosed as Annexure P [•].

(b)	On 23.05.2025, SRI3PL issued the force majeure notice to its beneficiaries under Article 11 of the respective PDAs notifying them about the force majeure event of collapse of 5 towers of the relevant transmission line which are enclosed as Annexure P [•].

(c)	SRI3PL wrote multiple letters to the Transmission Licensee - Renew Transmission Ventures Pvt Ltd and CTUIL for early restoration of towers so as to facilitate commissioning of 360.5 MW project in phases before 30.06.2025. The letters dated 27.05.2025 and 11.06.2025 from SRI3PL to Renew Transmission Ventures Private Limited are enclosed as Annexure P [•].

(d)	Finally, on 28.06.2025, the towers were restored.

113.	In view of the foregoing, it is submitted that as on the ISTS waiver cut-off date – 30.06.2025, SRI3PL was well placed to commission part capacity of 360.5 MW but could not commission the same in view of the above. Accordingly, in spite of its prudent efforts to mitigate delay in the SCOD of the Project, SRI3PL could not commission its Project on or before the ISTS waiver cut-off date.

114.	It is submitted that vide Report dated 11.06.2026, the Committee has specifically acknowledged that the delay in commissioning of SRI3PL's Project is also attributable to force majeure events including delay due to RoW issues, unprecedented rainfall, delay due to land acquisition and administrative delays [Para 8.1].

115.	Further, the Committee also reiterated that in terms of Regulation 13(2)(h), RE projects with SCOD on or before 30.06.2025, are eligible for 100% waiver of ISTS charges, if the delay in achieving SCOD is attributable to non-availability of transmission or other force majeure events.

E.	SRI3PL has acted diligently and made substantial progress with project work

116.	It is submitted that the Committee has also acknowledged that even as on the date of filing of the Application, SRI3PL has achieved substantial completion of the Project including, complete land aggregation for wind capacity, installation of substantial generation capacity, readiness of PSS and DTL, supply of requisite material and equipment, significant capital expenditure, etc. [Para 9.4].

117.	Till date, SRI3PL has incurred an expenditure of approximately Rs. 4241.93 Crores as of 31.08.2026. The certificate by SRI3PL's Chartered Accountant dated 03.09.2026 verifying the details of the expenditure incurred as on 31.08.2026 is annexed hereto and marked as Annexure P [•].

118.	These facts establish the Petitioners' bona fides and make it clear that the Project was being seriously implemented and only stood delayed due to external constraints affecting evacuation, approvals and regulatory transition.

F.	The Petitioners' case falls within Regulation 13(2)(h) of the Sharing Regulations

119.	The Petitioners submit that Regulation 13(2)(h), as amended, contemplates relief where delay in commissioning is attributable to non-availability of transmission system or other force majeure-type circumstances not attributable to the developer, subject to the applicable framework.

120.	The present case falls squarely within such framework because:

(a) 	The Project commissioning schedule was crystallised through contractual commitments with VAL, Sterlite Copper and Cairn India;

(b) 	SRIPL applied for connectivity sufficiently in advance;

(c) 	SRI3PL faced delayed operationalisation of connectivity and associated evacuation system beyond its control, including on account of the Narendra New line and the Gadag-Koppal line;

(d)	SRI3PL also faced uncertainty arising from the transition into the GNA framework and other reasons beyond its control,

(e)	SRI3PL nevertheless made substantial implementation progress

121.	Each of the principal causes of delay pleaded by SRI3PL is external to SRI3PL and bears directly upon the ability to commission and evacuate power from the Project. SRI3PL, therefore, satisfies the conditions for grant of extension for the purpose of maintaining eligibility for waiver of ISTS charges.

122.	The Addendum dated 14.01.2026 provides that the Committee shall give its recommendation in the form of a report to this Hon'ble Commission with a copy to the applicant, and that thereafter the concerned applicant shall approach this Hon'ble Commission through a miscellaneous petition along with the report of the Committee and relevant supporting documents. The present Petition has been filed in terms of the aforesaid procedural framework, i.e., pursuant to the Committee Report dated 11.06.2026, wherein it has been recommended that SCOD of the Project be extended up to 30.06.2026 (two 6 months extensions from 30.06.2025), or till date of commissioning of CTS / actual COD of balance capacity, whichever is earlier.

123.	The relief sought in the present Petition is confined to extension of the Project timeline / SCOD for the limited purpose of maintaining eligibility for waiver of ISTS charges as recommended by the Committee Report dated 11.06.2026.

124.	Without such relief, SRI3PL would be denied waiver eligibility despite having acted diligently and despite delay having arisen due to factors such as transmission non-availability, tower collapse, delayed statutory approval and regulatory transition that were wholly or substantially beyond its control.

125.	In the circumstances, SRI3PL is entitled to appropriate orders from this Hon'ble Commission in terms of Section 79(1)(c) read with Regulation 13(2)(h) of the Sharing Regulations.

VII.	Matters not previously filed or pending with any other court

126.	No matter has been filed by SRI3PL seeking the same reliefs as prayed for in the present Petition on the same cause of action before this Hon'ble Commission.

VIII.	Relief(s) sought

127.	In light of the facts and circumstances stated hereinabove, it is most respectfully prayed that this Hon'ble Commission may be pleased to:

(a) 	Hold and declare that the delay in commissioning of the 470 MW Hybrid (200 MW solar and 270 MW wind) power Project in Gadag, in the State of Karnataka is on account of various force majeure events, particularly the delay in commissioning of the evacuation/common transmission system associated with Gadag PS including the Narendra New (GIS) - Pune (GIS) 765kV D/C line and the Gadag PS - Koppal PS 400 kV D/C line, as also noted by the Committee vide Report dated 11.06.2026;

(b) 	Grant extension of the Scheduled Commercial Operation Date / commissioning timeline till 30.06.2026 for the 372 MW (146.87 MW Solar and 225.2 MW Wind) capacity of the Project in terms of the recommendations in the Report dated 11.06.2026 issued by the Committee such that the 470 MW capacity is eligible/entitled to 100% waiver from Inter-State Transmission System charges, as under:

(i) first extension from 30.06.2025 to 31.12.2025; and

(ii) second extension from 01.01.2026 to 30.06.2026,

(c)	Pass such further order(s) and / or direction(s) as this Hon'ble Commission may deem just and proper in the facts and circumstances of the present case.

IX. 	Interim reliefs sought, if any

128.	N/A

X. 	List of Enclosures

129.	As per the Index

XI. 	Proof of Payment

130.	The fee has been paid on bearing Transaction No.

Dated at                         on this               day of

Serentica Renewables India 3 Private

Limited / Petitioner No. 1

Serentica Renewables India Private

Limited / Petitioner No. 2

Filed by:

TRILEGAL

Advocate for the Petitioners

1st Floor, Wing A&B, Prius Platinum

D-3, District Centre, Saket,

New Delhi - 110017