BEFORE THE HON’BLE CENTRAL ELECTRICITY REGULATORY COMMISSION, NEW DELHI

PETITION NO. ________ / MP / 2026

IN THE MATTER OF:	Sembcorp Green Infra Limited

AND

IN THE MATTER OF:	Petition under Section 79 of the Electricity Act read with Regulation 19, 57 and 58 of the Central Electricity Regulatory Commission (Indian Electricity Grid Code) Regulations, 2023 (as amended) seeking extension of time for injection of infirm power in respect of 5 Wind Turbine Generators aggregating 10.5 MW forming part of the Petitioner’s 180 MW ISTS-connected Kanakagiribad Wind Power Project at Koppal, Karnataka under SECI Wind                 Tranche- XI, together with condonation / relaxation of the timeline for approaching this Hon’ble Commission under the proviso to Regulation 19(3).

AND

IN THE MATTER OF:

Sembcorp Green Infra Limited

(formerly Sembcorp Green Infra Private Limited,

Green Infra Wind Energy Private Limited and

Green Infra Wind Energy Limited)

Through its Authorised Representative,

Building 7A, Level 5,

DLF Cyber City, Gurugram,

Haryana – 122002

Phone No: + 91124 6846700/701

E-mail: Priya.dwivedi@sembcorp.com						…Petitioner

Versus

1. Southern Regional Load Despatch Centre (Grid Controller of India Limited),

Through its Executive Director

Grid Controller of India Limited

29, Race Course Cross Road,

Bengaluru – 560009, Karnataka

Phone No: + 91  80-22254525/22351146/22352850

E-mail:  tsrinivas@grid-india.in

…Respondent No. 1

2. Solar Energy Corporation of India Limited,

Through its Managing Director

6th Floor, Plate-B, NBCC Office Block Tower-2,

East Kidwai Nagar, New Delhi – 110023

Phone No: + 91  11 24666200

E-mail: corporate@seci.co.in	                                                                         …Respondent No. 2							…Respondent No. 2

3. Central Transmission Utility of India Limited,

Through its Chairman

Floors No. 5th-10th, IRCON International Tower, Tower 1,

Plot No. 16, Institutional Area, Sector 32,

Gurugram 122003 , Haryana

Phone No: + 91  124 2012900

E-mail: do@powergrid.in	                                                                          ...Respondent No. 3

...Respondent No. 3

PETITION UNDER SECTION 79 OF THE ELECTRICITY ACT, 2003 AND REGULATION 19, 57 AND 58 OF THE IEGC 2023

- Executive Summary of the Petition

- Brief background of the Petitioner

- The Petitioner, Sembcorp Green Infra Limited (“Petitioner” / “SGIL”) (formerly Sembcorp Green Infra Private Limited, and previously Green Infra Wind Energy Private Limited and Green Infra Wind Energy Limited), is a generating company within the meaning of Section 2(28) of the Electricity Act, 2003 (the Act), incorporated under the Companies Act, 2013, having its office at Building 7A, Level 5,  DLF Cyber City, Gurugram, Haryana – 122002 (Petitioner / SGIL). The Petitioner is developing a 180 MW Inter-State Transmission System (ISTS)-connected wind power project at Koppal, Karnataka, awarded under SECI Tranche-XI (“Project”), whereby power will be evacuated at the 220 kV level of the 400/220 kV Gadag Pooling Station.

- Brief background of the Respondents

- Respondent No. 1 is the Southern Regional Load Despatch Centre (“SRLDC” / “Respondent No. 1”), which is operating as a wing of Grid Controller of India Limited, is the Regional Load Despatch Centre exercising operational jurisdiction over the Project.

- Respondent No. 2, Solar Energy Corporation of India Limited (“SECI”), is the procurer and counter-party to the Power Purchase Agreement dated 26.08.2022 (as amended) executed with the Petitioner in respect of the Project. It is submitted that Respondent No. 2 has been impleaded as a proforma party and SGIL is not claiming any relief qua SECI.

- Respondent No. 3, Central Transmission Utility of India Limited (“CTUIL”), granted the Petitioner its connectivity, Long-Term Access (LTA) and General Network Access (GNA) related approvals. It is submitted that Respondent No. 3 has been impleaded as a proforma party and SGIL is not claiming any relief qua CTUIL.

- Brief background of the matter

- The present Petition is filed praying for this Hon’ble Commission to grant an extension of time of 4 (four) months for the injection of infirm power in respect of 5 Wind Turbine Generators (WTGs) aggregating 10.5 MW forming part of the Project, namely KKBKA035, KKBKA065, KKBKA112, KKBKA300 and KKBKA305. These 5 WTGs could not complete the repeat trial run within the 135 -day window prescribed under the Central Electricity Regulatory Commission (Indian Electricity Grid Code) Regulations, 2023 (“IEGC 2023”) (as amended) on account of a supervening events which were beyond the control of the Petitioner and form sufficient basis for exercise of power (akin to Force Majeure event), together with condonation / relaxation of the timeline for approaching this Hon’ble Commission under the proviso to Regulation 19(3) of the IEGC 2023.

- It is submitted that out of the total capacity of 180 MW for the Project, comprising  86 No. of WTGs, 47 No. of WTGs aggregating 98.7 MW already stand commissioned, the repeat trial run to be conducted only for the 10.5 MW and the remaining 70.8 MW will be commissioned progressively .

- The salient factual background for the Petition is as under:-

(a)	Respondent No. 1 issued two FTC approvals as under:-

i.	FTC Approval dated 10.02.2026 for 25.2 MW (12 WTGs), permitting injection of infirm power from 11.02.2026 to 27.03.2026;

ii.	FTC approval dated 12.02.2026 for 14.7 MW (7 WTGs), permitting injection of infirm power from 13.02.2026 to 29.03.2026.

Thus, for a total capacity of 39.9 MW (comprising 19 WTGs), FTC was issued permitting injection of infirm power.

(b)	Trial-run operations were conducted on 24.02.2026 and 14.03.2026 for the full 39.9 MW comprising 19 WTGs. Trial run succeeded for 29.4 MW (14 WTGs), for which Respondent No. 1 issued a Successful Trial Run Certificate dated 13.05.2026. However, the trial run for the balance 10.5 MW (5 WTGs) failed on account of low wind conditions and required a repeat trial run.

(c)	On 17.05.2026, before the repeat trial run could be conducted, 5 (five) 220 kV transmission towers of the Kanakagiribad PSS-Gadag PS line collapsed and a sixth transmission tower was left bent during a storm of gusty winds, rain, lightning and thunderstorms, severing the sole evacuation path of the Project and forcing a complete shutdown that lasted until the line was restored on 28.06.2026.

(d)	On 18.05.2026, the Petitioner had intimated Respondent No. 1 of the collapse of the transmission towers and had issued a Force Majeure Notice dated 02.06.2026 and sought a 45-day extension (from 27.06.2026 to 11.08.2026) to inject infirm power for the balance 10.5 MW.

(e)	On 09.06.2026, Respondent No. 1 replied to the Petitioner clarifying that Respondent No. 1 could grant extension only up to 26.06.2026 under the IEGC 2023, being 135 days from FTC approval, and that any extension beyond that date can only be granted by this Hon’ble Commission in terms of the IEGC.

- Accordingly, it is the Petitioner’s case that:-

- FTC was granted by Respondent No. 1 for a total capacity of 39.9 MW (comprising 19 WTGs), FTC was issued permitting injection of infirm power. As per the IEGC 2023, a period of 45 days is granted for injection of infirm power post receipt of FTC.

- The period of 45 days can be extended by the relevant regional load despatch centre by a period of 3 months (i.e. total of 135 days from FTC) under the IEGC 2023.

- The proviso to Regulation 19(3) of the IEGC 2023, states that an extension of the period for injection of infirm power the period of beyond three months can be granted only by this Hon’ble Commission upon an application made by the generating station along with detailed reasons as reproduced below:-

“19. Drawal of Start Up Power and Injection of Infirm

…

(3) Notwithstanding the provisions of clause (2) of this Regulation, the Commission may allow extension of the period for inter-change of power beyond the stipulated period on an application made by the generating station at least two months in advance of the completion of the stipulated period.”

- The Petitioner was precluded from completing the repeat trial run and from injecting infirm power in respect of the 5 WTGs solely on account of a supervening events beyond the control of the Petitioner and which completely prevented the Petitioner from completing its obligation/trial run, namely the collapse of five 220 kV transmission towers and the bending of one 220 kV transmission tower on the sole evacuation line of the Project on 17.05.2026, an event wholly beyond the Petitioner's control and incapable of prevention despite the exercise of all prudent utility practices.

- It is pertinent to note that while the IEGC 2023 does not itself contain any force majeure provision, the said event is therefore relied upon as the factual foundation for the exercise of this Hon'ble Commission's powers under Regulations 19(3), 57 and 58 as this Hon'ble Commission itself clarified in Order dated 23.03.2026 in Petition No. 34/MP/2026 titled TEQ Green Power XI (P) Ltd. v. WRLDC ("TEQ Order dated 23.03.2026"), holding that such events are "only acknowledged to allow extension of infirm power injection under Regulation 19(3) … not otherwise".

“ 19. Drawal of Start Up Power and Injection of Infirm

…

(3) Notwithstanding the provisions of clause (2) of this Regulation, the Commission may allow extension of the period for inter-change of power beyond the stipulated period on an application made by the generating station at least two months in advance of the completion of the stipulated period.”

- Regulation 57 (Power to Relax) of the IEGC 2023 empowers this Hon'ble Commission, on the application of an affected person, to relax any provision so as to remove hardship, and this power ought to be exercised in the present facts, the Petitioner having been prevented from completing the trial run and from injecting infirm power for reasons wholly beyond its control and not attributable to it. Pertinently, this Hon'ble Commission has exercised this very power, upon materially similar facts, vide Order dated 23.03.2026 in Petition No. 34/MP/2026 titled TEQ Green Power XI (P) Ltd. v. WRLDC ("TEQ Order dated 23.03.2026") and Order dated 14.11.2025 in Petition No. 854/MP/2025 titled NTPC Renewable Energy Ltd. v. WRLDC & Ors. ("NTPC Order dated 14.11.2025"), condoning the delay and granting an extension under Regulation 19(3) so that, in the words of this Hon'ble Commission, "RE capacity, which is ready to be charged and start generation, should not be stranded".

- Further, the delay and period in approaching this Hon’ble Commission deserves to be relaxed and/or condoned in the exercise of this Hon'ble Commission's Power to Relax under Regulation 57 of the IEGC 2023 read with Regulation 65 of the CERC (Conduct of Business) Regulations, 2023 as the very occasion to approach this Hon'ble Commission was crystallised only upon restoration of the evacuation infrastructure on 28.06.2026;

- Further, this Hon’ble Commission has the power to suo-moto pass directions in exercise of Regulation 58 (Power to Remove Difficulty), read with Regulation 60 of the IEGC 2023 to permit the Petitioner to inject infirm power for the 5 WTGs; and

- No prejudice whatsoever will be caused to any party and grant of extension in injection of infirm power is required given that the Project is a must-run renewable station of which 98.7 MW has already achieved COD and the relief prayed for is narrow and  confined to the 5 WTGs, and does not entail any rewriting of Regulation 19 of the IEGC 2023.

- Reliefs Sought in brief

- The reliefs sought are set out in the parts of the present Petition titled ‘Relief(s) sought’ and ‘Interim reliefs sought, if any’.

- DETAILED PETITION

- Jurisdiction of the Commission

- It is submitted that the IEGC 2023 has been notified by this Hon’ble Commission in exercise of the powers conferred by Section 79(1)(h) read with Section 178 of the Electricity Act, 2003 and the present Petition seeks exercise of powers granted under the IEGC 2023 itself.

- It is submitted that the proviso to Regulation 19(3) of the IEGC 2023, as inserted by the First Amendment Regulations, 2024, expressly provides that, for Renewable Energy Generating Stations (REGS), an extension of the period for injection of infirm power beyond 135 Days (45 Days + three  months) may be allowed only by this Hon’ble Commission. Thus, the present Petition, which seeks exactly this extension, falls squarely and exclusively within the jurisdiction of this Hon’ble Commission.

- It is further submitted that this Hon’ble Commission is independently empowered under Regulation 57 (Power to Relax) and Regulation 58 read with Regulation 60 (Power to Remove Difficulty, and Issue of Suo Motu Orders and Directions) of the IEGC 2023 to grant the reliefs prayed for herein. Pertinently, Respondent No. 1 has itself, by its reply dated 09.06.2026, directed the Petitioner to approach this Hon’ble Commission.

- In view of the above, this Hon’ble Commission has the jurisdiction to entertain and adjudicate the present Petition and to pass appropriate orders and directions.

- Details of the documents based on which the petition is made

- The documents forming part of and relied upon in the present Petition are mentioned in the List of Enclosures / Index of Enclosures.

- Limitation

- It is submitted that the present Petition is within time. The occasion for the Petitioner to approach this Hon’ble Commission crystallised only upon Respondent No. 1’s reply dated 09.06.2026, whereby the Petitioner was, for the first time, informed that an extension beyond 135 days from FTC approval lay outside the purview of the RLDC and required the approval of this Hon’ble Commission. The Petition has been filed thereafter, following the restoration of the transmission line and issuance of the FTC Approval & charging code on 28.06.2026.

- It is submitted that, to the extent the proviso to Regulation 19(3) contemplates an application to this Hon’ble Commission at least 15 days in advance of the completion of the stipulated period, that window fell squarely within the period in which the evacuation line lay collapsed and restoration was still under way, so that compliance was rendered impracticable by the very Force Majeure event that is the subject of this Petition. In the premises, there is no delay, laches or acquiescence on the part of the Petitioner, and the requirement of advance filing may be relaxed / condoned for the reasons set out in the Petition.

- Facts of the Case

Re:	The applicable regulatory framework

- On 11.07.2023, this Hon’ble Commission notified the IEGC 2023. It is submitted that the present dispute arises within the framework of Regulation 19 of the IEGC, 2023, which governs the drawal of start-up power and the injection of infirm power and seeks exercise of power granted under Regulation 57-58 of the IEGC 2023. The relevant provisions of the IEGC 2023 are reproduced below:-

“19. DRAWAL OF START UP POWER AND INJECTION OF INFIRM POWER

(1) A unit of a generating station … granted connectivity to the inter-State Transmission System in accordance with GNA Regulations shall be allowed to inter-change power with the grid during the commissioning period, including testing and full load testing before the COD, after obtaining prior permission of the concerned Regional Load Despatch Centre …

(2) The period for which such inter-change shall be allowed shall be as follows: - … (b) Injection of infirm power shall not exceed one year from the date of first synchronization.

(3) Notwithstanding the provisions of clause (2) of this Regulation, the Commission may allow extension of the period for inter-change of power beyond the stipulated period on an application made by the generating station at least two months in advance of the completion of the stipulated period …

[…]

57. POWER TO RELAX. The Commission, for reasons to be recorded in writing, may relax any of the provisions of these regulations on its own motion or on an application made before it by an affected person to remove the hardship arising out of the operation of any of these regulations, applicable to a class of persons.”

“58. POWER TO REMOVE DIFFICULTY. If any difficulty arises in giving effect to the provisions of these regulations, the Commission may, on its own motion or on an application made before it by the nodal agency, by order, make such provisions not inconsistent with the provisions of the Act or provisions of other regulations specified by the Commission, as may appear to be necessary for removing the difficulty in giving effect to the objectives of these regulations.”

“60. ISSUE OF SUO MOTO ORDERS AND DIRECTIONS. The Commission may from time to time issue suo motu orders and practice directions with regard to implementation of these regulations and matters incidental or ancillary thereto, as the case may be.”

- On 23.10.2024, this Hon’ble Commission notified the Central Electricity Regulatory Commission (Indian Electricity Grid Code) (First Amendment) Regulations, 2024 (published in the Gazette of India on 29.10.2024), which substituted Regulation 19(2)(b), introduced Regulation 19(2)(c), and added a proviso to Regulation 19(3) as under:-

“(c) Injection of infirm power shall not exceed 45 (forty-five) days from the date of first-time energization and integration (FTC) approval for REGS and ESS (except Hydro PSP ESS).”

“Provided that for REGS and ESS (except Hydro PSP ESS), extension of period for injection of infirm power beyond the stipulated period may be allowed (a) for a period up to three months by respective RLDC on an application(s) … at least 10 days in advance of the completion of the stipulated period, (b) for a period beyond three months, by the Commission on an application(s) … at least 15 days in advance of the completion of the stipulated period.”

Copies of the relevant extracts of the IEGC, 2023 and the First Amendment Regulations, 2024 are annexed hereto and marked as Annexure P-1 (Colly).

Re:	Project and connected connectivity and Power Purchase Agreement

- On 20.08.2021, the Petitioner submitted an application (Application No. 1200003413) to CTUIL seeking grant of Stage-I Connectivity for a total capacity of 500 MW under the CERC (Grant of Connectivity, Long-term Access and Medium-term Open Access) Regulations, 2009 (as amended). A Copy of the Application for Grant of Stage-I Connectivity dated 20.08.2021 is annexed hereto and marked as Annexure P-2.

- On 21.10.2021, SECI issued its Letter of Award (“LOA”) in the Petitioner’s favour for a 180 MW ISTS-connected wind power project under SECI Tranche-XI. A copy of the LOA dated 21.10.2021 issued by SECI to the Petitioner for the Project is annexed hereto and marked as Annexure P-3.

- On 21.10.2021, The Petitioner submitted Stage-II Connectivity Application No. 1200003500 to CTUIL seeking Stage-II Connectivity for 180 MW at Gadag Pooling Station, based on the LOA issued by the Solar Energy Corporation of India Limited ("SECI") under SECI Tranche-XI. A Copy of the Application for Grant of Stage-II Connectivity dated 21.10.2021 is annexed hereto and marked as Annexure P-4.

- On 29.12.2021, CTUIL issued the intimation for grant of Stage-II Connectivity to SGIPL for 180 MW at Gadag Pooling Station against Application No. 1200003500 dated 21.10.2021, based on the SECI Tranche-XI Letter of Award. A copy of the grant of Stage-II Connectivity for 180 MW by CTUIL dated 29.12.2021 is annexed hereto and marked as Annexure P-5.

- On 29.07.2022, the Petitioner submitted LTA Application No. 0451100007 to CTUIL seeking Long-Term Access for 178.5 MW for transfer of power from Gadag Pooling Station, Karnataka to beneficiaries in Chhattisgarh & Madhya Pradesh (Western Region) and Uttar Pradesh (Northern Region) under the SECI Tranche-XI arrangement. A copy of the LTA Application dated 29.07.2022 is annexed hereto and marked as Annexure P-6.

- On 26.08.2022, the Petitioner and SECI executed the Power Purchase Agreement (“PPA”) for supply of 178.5 MW from the Project. The capacity was enhanced to 180 MW by way of Amendment No. 1 dated 15.11.2022. Subsequent amendments including Amendment No. 2 dated 14.01.2025 were executed to record change in the name of the Petitioner and incorporate the revised the commissioning timelines. On 11.05.2026 , the Amendment No. 3 to the PPA was executed which recorded change in the name of the Petitioner and revised the Scheduled Commissioning Date of the Project to the earlier of 60 days from the operationalisation of GNA / connectivity at Gadag PS or 30.06.2026. A copy of the PPA dated 26.08.2022 (along with all amendments) is annexed hereto and marked as Annexure P-7 (Colly).

- On 14.10.2022, CTUIL issued the grant of Long-Term Access for 178.5 MW to the Petitioner against LTA Application No. 0451100007 dated 29.07.2022, for transfer of 178.5 MW from Gadag Pooling Station to SECI Tranche-XI beneficiaries. A copy of the grant of the LTA by CTUIL dated 14.10.2022 is annexed hereto and marked as Annexure P-8.

- On 09.11.2022, the Petitioner executed the LTA Agreement with CTUIL formalising the grant of LTA for 178.5 MW at Gadag Pooling Station. A copy of the LTA application dated 29.07.2022 and the LTA Agreement dated 09.11.2022 is annexed hereto and marked as Annexure P-9(Colly).

- On 06.12.2022, the Petitioner filed LTA Application seeking 1.5 MWLTA at Gadag Pooling Station.

Re:	Transition to General Network Access

- It is submitted that, upon the coming into force of the CERC (Connectivity and General Network Access to the Inter-State Transmission System) Regulations, 2022 (“GNA Regulations”), the Petitioner undertook the required transition of its access to the GNA regime.

- On 02.05.2023, The Petitioner submitted transition request to CTU seeking transition of Connectivity from the Connectivity Regulations, 2009 to the GNA Regulations for various application including the balance 1.5 MW (Application No. 1670310631002), as required under Regulation 37 of the GNA Regulations, 2022. Consequently, the Petitioner inter-alia filed parallel conversion applications under the GNA Regulations, 2022 to restructure its firm connectivity into distinct GNA grants which included conversion of 178.5 MW under Regulation 37.3 and conversion of 1.5 MW under Regulation 37.1 of the GNA Regulations (aligned to the SECI-XI PPA capacity).

- On 18.08.2023, 21st Consultation Meeting for Evolving Transmission Schemes – Southern Region (“21st CMETS-SR”) was convened and approved the restructuring of   the Petitioner’s connectivity under the GNA Regulations, 2022, formally recognizing inter-alia the conversion of 178.5 MW under Regulation 37.3 and 1.5 MW under Regulation 37.1 of the GNA Regulations. Accordingly, a conversion letter on 21.09.2023 for 178.5 MW and final grant on 08.03.2024 for 1.5 MW  connectivity was issued to the Petitioner . Copies of the transition correspondence, the minutes of the 21st CMETS-SR meeting held on 18.08.2023 and the final grants of connectivity dated 08.03.2024 are annexed hereto and marked as Annexure P-10 (Colly).

- On 14.05.2024 and 04.07.2024, CTUIL recorded change of name of the grantee from Green Infra Wind Energy Limited (“GIWEL”) to Green Infra Wind Energy Private Limited ("GIWEPL") and subsequently to “Sembcorp Green Infra Private Limited”  (“SGIPL”) across all connectivity/LTA/GNA grants and applications. Annexure P-11 (Colly).

Re:	Commissioning of the Project

- It is submitted that the Petitioner began the commissioning activities for the Project in phases and accordingly achieved COD as under:-

(a)	Part-capacity of 54.6 MW – COD achieved on 17.01.2025;

(b)	Part-Capacity of 14.7 MW  - COD achieved / PPA compliance on 25.03.2026;

(c)	Part-Capacity 29.4 MW – COD achieved / PPA compliance on 22.05.2026.

Accordingly, at present, 98.7 MW now stands in commercial operation, with the 10.5 MW awaiting its repeat trial run, and the remaining 70.8 MW will be commissioned progressively. Copies of the COD / PPA-compliance certificates for the 54.6 MW, 14.7 MW and 29.4 MW part-capacities are annexed hereto and marked as Annexure P-12 (Colly).

Re:	The FTC approvals, Trial Run and the failure of balance 5 WTGs

- On 10.02.2026, Respondent No. 1 issued FTC approval for 25.2 MW comprising 12 turbines, permitting charging, and injection of infirm power from 11.02.2026 to 27.03.2026. Further, on 12.02.2026, Respondent No. 1 issued FTC approval for 14.7 MW comprising 7 turbines, permitting the same from 13.02.2026 to 29.03.2026. Thus, FTC approval for 39.9 MW. Copies of the FTC applications and the FTC approvals dated 10.02.2026 and 12.02.2026 are annexed hereto and marked as Annexure P-13 (Colly).

- On 24.02.2026and 14.03.2026, the Petitioner conducted trial-run operations for the full 39.9 MW comprising 19 turbines.

- On 13.05.2026, Respondent No. 1 issued Successful Trial Run Certificate for 14 (Fourteen) WTGs aggregating to 29.4 MW which had cleared the trial run. The remaining five WTGs — KKBKA035, KKBKA065, KKBKA112, KKBKA300 and KKBKA305, together 10.5 MW could not complete the trial run on the account that wind during their test was too low to demonstrate the required output. It is noteworthy that prior to the event of the tower collapsing on 17.05.2026, the Petitioner had already undertaken the necessary remedial measures and the balance 5 WTGs were ready for repeat trial run. The repeat trial run could not thereafter be conducted solely on account of  the unavailability of the evacuation corridor arising from collapse of the evacuation towers. Accordingly, a repeat trial run was called for. A copy of the Successful Trial Run Certificate dated 13.05.2026 issued by Respondent No. 1 is annexed hereto and marked as Annexure P-14.

Re:	Supervening Event impacting the Petitioner

- On 17.05.2026 (at 16:16 Hrs.) and before the Petitioner could conduct the repeat trial run for the balance 10.5 MW, the Kanakagiribad PSS-Gadag PS 220 kV line tripped solely on account of extreme gusty winds, rain, lightning and thunderstorms. An initial attempt to re-charge the line (under charging code 2560) failed and the line tripped again, whereupon a site inspection revealed that five 220 kV transmission towers had collapsed and a sixth had been left bent, near Kushtagi in Koppal District which was 10–12 km from the pooling station. Further, site visit and examination also revealed that a crane deployed at a neighbouring wind project toppled the same day in the same weather.

- On 18.05.2026, the Petitioner intimated Respondent No. 1 of the incident and the impact. Copy of email dated 18.05.2026 from the Petitioner to the Respondent along with related correspondence establishing collapse of towers are annexed hereto and marked as Annexure P-15 (Colly)

- It is submitted that the failure was grave enough to draw a joint site inspection by a Standing Committee of Experts drawn from the CEA, SRPC,  PGCIL and KPTCL. Email communication with the CEA is annexed hereto and marked as Annexure P-16.

- It is submitted that, with the collapse of the towers, the sole evacuation path of the Project became unavailable and the Project fell into complete shutdown. The Petitioner was unable to evacuate power even from its commissioned capacity and suffered a generation loss of approximately 69.3 MW from 17.05.2026 and 98.7 MW from 24.05.2026 until the restoration of the 220 kV transmission line towers on 28.06.2026.

Re:	The Petitioner’s request to Respondent No. 1 and the direction to approach the Commission

- On 02.06.2026, the Petitioner issued a Force Majeure Notice to the Respondent No. 1 basis the tower collapse and inability to evacuate power and requested Respondent No. 1 to extend the time to inject infirm power for the balance 10.5 MW for period of  45 days from 27.06.2026 to 11.08.2026, that being the estimated period to restore the line together with the days required to ready the turbines. A copy of the Force Majeure Notice dated 02.06.2026 is annexed hereto and marked as Annexure P-17

- On 09.06.2026, Respondent No. 1 replied to the Petitioner and inter-alia stated that:-

(a)	As per Regulation 19 of the IEGC 2023 (As amended), injection of infirm power was permitted under the IEGC 2023 from 11.02.2026 to 27.03.2026 (i.e. 45 days from FTC approval);

(b)	Respondent No. 1 can grant extension only up to 26.06.2026, being 135 days from FTC approval (i.e. 45 days + 3 months); and

(c)	Any extension beyond 135 days did not fall within the purview of the RLDC and required the approval of this Hon’ble Commission.

(d)	Respondent No. 1 accordingly directed the Petitioner to approach this Hon’ble Commission.

A copy of the SRLDC reply dated 09.06.2026 is annexed hereto and marked as Annexure P-18.

- On 28.06.2026, the 220 kV transmission line was restored post completion of requisite rectification works and obtaining requisite CEA safety clearance and receipt of FTC Approval & charging code. Only post this could the Petitioner seek to approach the FTC clearance from Respondent No. 1

- It is submitted that the period permitted under the IEGC 2023 for grant of extension in injection of  infirm power by Respondent No. 1 (i.e. till 26.06.2026 being  135 days from grant of FTC) lapsed during the period wherein the Force Majeure Event was subsisting. Accordingly, as a result, the Petitioner was, for reasons wholly beyond its control, unable to make the advance application to this Hon’ble Commission contemplated by the proviso to Regulation 19(3). Copies of the line-restoration and 220 kV charging-code correspondence dated 28.06.2026 are annexed hereto and marked as Annexure P-19 (Colly).

- It is further submitted that the very purpose of permitting injection of infirm power is to facilitate the testing, trial operation, and commissioning of the generating station prior to commencement of regular operations. In the present case, the Petitioner had substantially completed the testing and commissioning activities, with only limited commissioning-related activities remaining to be undertaken. The generating station is otherwise ready for operationalisation and was denied completion of testing/trial operation solely on account of events beyond the Petitioner’s control. , and the inability to complete the residual activities and seek the requisite extension arose solely on account of the Force Majeure Event beyond the Petitioner's control. In these circumstances, any denial of extension by this Hon’ble Commission would defeat and frustrate the underlying object and purpose of Regulation 19 of the IEGC, which is to enable a generating station to complete the commissioning process and achieve commercial readiness.

- Facts in Issue and Questions of Law

- The facts in issue are as enumerated hereinabove from Paragraph [•] to Paragraph [•]. In view thereof, the following Questions of Law arise for the consideration of this Hon’ble Commission: —

- Whether the collapse of the evacuation line on 17.05.2026, constitutes an event beyond the control of the Petitioner which directly and solely led to the failure of the Petitioner to complete the repeat trial run and to inject infirm power within the stipulated period and whether such event can be considered as a sufficient basis to exercise power under Regulation 19(3) of the IEGC 2023?

- Whether this Hon’ble Commission ought to grant an extension of time for the injection of infirm power in respect of the balance 5 WTGs aggregating 10.5 MW, under the proviso to Regulation 19(3) of the IEGC, 2023?

- Whether this Hon’ble Commission ought to relax/condone the delay in approaching this Hon’ble Commission in view of the timeline of 15 days prior to expiry of scheduled time provided under Regulation 19(3) of the IEGC 2023?

- Whether this Hon’ble Commission ought to exercise Power to Relax under Regulation 57, and Power to Remove Difficulty under Regulation 58 read with Regulation 60, of the IEGC 2023?

- SUBMISSION

A.	This Hon’ble Commission ought to grant extension in exercise of Regulation 19 of IEGC 2023

- At the outset, it is submitted that the scheme of Regulation 19 of the IEGC 2023 furnishes a complete answer to the present case inasmuch as:-

(a)	Regulation 19(2)(c) provides that, in the case of a Renewable Energy Generating Station (“REGS”), the injection of infirm power shall not exceed forty-five days from the date of FTC approval.

(b)	The proviso to Regulation 19(3) permits the concerned RLDC to grant an extension of up to three months; and

(c)	The proviso to Regulation 19(3) also expressly provides that any extension beyond three months can be granted only by this Hon’ble Commission, upon an application made with detailed reasons at least fifteen days in advance of the completion of the stipulated period.

- Thus, it is submitted that the regulatory scheme categorically contemplates that, in a deserving case, the injection of infirm power may be permitted beyond the aggregate period of one hundred and thirty-five days at the discretion to this Hon’ble Commission. The present case is one such deserving case as detailed in the present Petition, wherein substantial investment has already been made by the Petitioner towards the development and commissioning of the Project, and the Project has reached an advanced stage. In these circumstances, refusal to grant the requested extension would result in disproportionate hardship to the Petitioner by rendering ineffective the significant investments already incurred and impeding the completion of the Project despite the Petitioner having substantially progressed towards operationalisation.

- It is submitted that this very reading of Regulation 19(3) has been consistently adopted by this Hon’ble Commission in the NTPC Order dated 14.11.2025 and the TEQ Order dated 23.03.2026 wherein this Hon’ble Commission, having set out Regulation 19(3), held as under:-

“As per the above, the extension for injection of infirm power beyond three months from the approval by [R]LDC is to be provided by the Commission, and an application for such a request is to be made 15 days in advance of the completion of the stipulated period.”

- It is submitted that the Petitioner’s case falls squarely within the said reservation. Pertinently, Respondent No. 1 has raised no objection whatsoever upon the merits of the Petitioner’s request, nor upon the score of grid security. The response by Respondent No. 1 is confined to the outer limit of its own jurisdiction.

- It is to be noted that there is no correspondence/document on record which points to any fault, default or want of diligence on the part of the Petitioner, or any risk to the secure operation of the grid. In these circumstances, it is respectfully submitted that the present Petition is maintainable and within the scope of Regulation 19(3) of the IEGC 2023.

B.	This Hon’ble Commission ought to exercise power under Regulation 19(3) and permit extension of time for injection of infirm power

B1.	The supervening event (Force Majeure) is sufficient factual foundation for exercise of power by this Hon’ble Commission under Regulations 19(3), 57 and 58 of IEGC 2023

- At the outset, it is submitted that under the IEGC 2023 (as amended), there is no force majeure provision. Accordingly, the IEGC 2023 does not make any provision for force majeure as basis for the non-performance / non-compliance of the obligations and requirements set out by this Hon’ble Commission under the IEGC including any claim for automatic extension of any prescribed timeline on that account.

- It is submitted that such an event is relevant for this Hon’ble Commission to take note of a compelling factual foundation for this Hon’ble Commission to exercise powers, namely, the power to grant an extension under Regulation 19(3), the Power to Relax under Regulation 57, and the Power to Remove Difficulty under Regulation 58 available under the IEGC 2023.

- It is submitted that this approach has been affirmed by this Hon’ble Commission in the TEQ Order dated 23.03.2026 wherein this Hon’ble Commission was considering the delay in injection of infirm power which have been occasioned by an unprecedented monsoon and by law-and-order disturbances at the project site. In view of the factual position, this Hon’ble Commission granted relief under Regulation 19(3) read with Regulation 57 and clarified as under:-

“The events impacting commissioning activities are only acknowledged to allow extension of infirm power injection under Regulation 19(3) of the Grid Code, not otherwise.”

- Accordingly, the Petitioner advances the same principle and invokes the events of 17.05.2026 as the factual predicate for this Hon’ble Commission to exercise its power under Regulations 19(3), 57 and 58 of the IEGC 2023.

- It is submitted that the Petitioner was prevented from undertaking the repeat trial run solely on account of events beyond its control, i.e. gusty winds, incessant rain, lightning and thunderstorms on 17.05.2026 which resulted in the collapse of 5 (five) 220 kV transmission towers and bending of a 6th (sixth) transmission tower of the Kanakagiribad PSS-Gadag PS line near Kushtagi.

- It is submitted that the collapse of the transmission towers resulted in the immediate and absolute sever of the power evacuation infrastructure available for the Project. The seriousness of the events is also corroborated by the collapse of a crane deployed at a neighbouring wind project on the same day and during the same events. Pertinently, this failure was considered grave enough to warrant a joint site inspection by a Standing Committee of Experts drawn from the CEA, SRPC, PGCIL and KPTCL.

- It is submitted that the 5 WTGs had already failed the trial run for want of adequate wind and were awaiting a repeat trial run within the time allowed under the IEGC 2023. However, from 17.05.2026 till 28.06.2026, the Petitioner was rendered wholly incapable both of evacuating power and of testing the WTGs, owing solely to the collapse of the transmission towers rendering the evacuation line inoperable.

- Pertinently, it is submitted that during this period, the performance of the Petitioner’s obligations under the IEGC were rendered physically impossible. It is submitted that the circumstances were of a greater degree that the monsoon conditions and the law-and-order disturbances which were considered by this Hon’ble Commission for grant of extension of time for injection of infirm power in the TEQ Order dated 23.03.2026 and the NTPC Order dated 14.11.2025.

B2.	This Hon’ble Commission ought to relax the requirement of 15 days advance application and condone the delay in filing of the present Petition.

- It is submitted that the proviso to Regulation 19(3) requires that an application (i.e. the present Petition) be filed before this Hon’ble Commission at least 15 days in advance of the completion of the stipulated period. It is submitted that that for the Petitioner, the stipulated period ended on 26.06.2026. Thus, the stipulated period lapsed while the evacuation infrastructure was still unavailable, and the Petitioner was consumed with restoration.

- It is submitted that the stipulation of applying before this Hon’ble Commission 15 days in advance ought to be relaxed/condoned by this Hon’ble Commission. It is submitted that the time period prescribed under Regulation 19(3) may be considered as directory by this Hon’ble Commission and ought not to prevent a genuine party from approaching this Hon’ble Commission whose very ability to comply was compromised by a supervening event. Further, it is a settled principle that a stipulation of time, framed in aid of orderly administration, is directory in character.

- Accordingly, it is submitted that the Petitioner is seeking relaxation of a procedural timing requirement in a regulatory proceeding which falls squarely within the discretion and power of this Hon’ble Commission given that the very occasion to approach this Hon’ble Commission was crystallised only post 28.06.2026, whereupon the Petitioner moved without delay.

- It is submitted that this Hon’ble Commission has, in both the TEQ Order dated 23.03.2026 and the NTPC Order dated 14.11.2025 condoned precisely such a delay in the exercise of its Power to Relax under Regulation 57 of the IEGC, 2023 read with Regulation 65 of the CERC (Conduct of Business) Regulations, 2023. In TEQ Order dated 23.03.2026, the petition there had been filed beyond the period prescribed by the proviso to Regulation 19(3) and this Hon’ble Commission held as under:-

“Considering the submissions made by the Petitioner regarding the factors cited as being beyond its control, it is observed that the circumstances leading to the delay were outside the Petitioner’s reasonable control. This Commission therefore condones a delay in filing of the Petition.”

- It is submitted that an identical course was adopted by this Hon’ble Commission in the NTPC Order dated 14.11.2025 wherein a delay of about one month in the filing of the petition came to be condoned in the exercise of the Power to Relax.

- Accordingly, it is submitted that this Hon’ble Commission ought to exercise power under Regulation 19(3) to grant extension of time of 4 months from date of order for injection of infirm power and condone the delay in approaching this Hon’ble Commission.

C.	This is a fit case for the exercise of the Power to Relax under Regulation 57 of the IEGC, 2023

- It is submitted that Regulation 57 of the IEGC, 2023 empowers this Hon’ble Commission, to relax any of the provisions of the IEGC 2023 upon an application made before it by an affected person, so as to remove the hardship arising out of the operation of the IEGC 2023. The delay in commissioning is solely attributable to the events beyond the control of the Petitioner (Force Majeure events) and thus warrants relaxation under Regulation 57 which provides as under:

“57. The Commission, for reasons to be recorded in writing, may relax any of the provisions of these regulations on its own motion or on an application made before it by an affected person to remove the hardship arising out of the operation of any of these regulations, applicable to a class of persons.”

- It is submitted that the Petitioner is an affected person within the meaning of the said provision and is suffering hardship qua the time period prescribed for injection of infirm power for reasons beyond its control. The factual position described in the present Petiiton falls within the scope and applicability of the hardship that Regulation 57 is designed to relieve.

- It is submitted that to decline the extension sought would result in the Petitioner’s Project being stranded that is ready in every respect save for a repeat trial run rendered impossible by force majeure conditions and would thereby defeat the very object of the orderly integration of renewable energy that the IEGC 2023 is intended to serve.

- It is submitted that this Hon’ble Commission has, in the TEQ Order dated 23.03.2026 and the NTPC Order dated 14.11.2025 exercised its Power to Relax under Regulation 57 to grant precisely the relief now sought, on materially similar facts. In the TEQ Order, a 151.2 MW wind power project had commissioned a substantial portion of its capacity, being thirty-six of its fifty-six WTGs, and only 4 WTGs aggregating 10.8 MW remained to be commissioned. Further, the concerned RLDC had exhausted the one hundred and thirty-five day ceiling and the delay had been occasioned by an unprecedented monsoon and by law-and-order disturbances at the site. Upon these facts, this Hon’ble Commission proceeded to condone the delay and, in the exercise of its powers under Regulation 19(3), to grant an extension of the period for the interchange of power up to one month from the date of the order and held as follows: —

“… the instant case is fit for exercising the Power to Relax to condone delay in filing of Petition and further grant extension to inject infirm power as per Regulation 19(3) of the 2023 Grid Code so that RE capacity, which is ready to be charged and start generation, should not be stranded.”

- Further, it is submitted that this Hon’ble Commission also adopted an identical course in the NTPC Order dated 14.11.2024 which was concerned with the non-commissioned elements of the 4,750 MW Khavda Solar Park and wherein the delay had been occasioned by extraordinary monsoon rains and by regional hostilities. It is submitted that even in that situation, this Hon’ble Commission, held the case to be a fit one for the exercise of the Power to Relax so that ready renewable capacity “should not be stranded”, condoned the delay, and granted an extension of up to two months under Regulation 19(3). It is to be noted that this Hon’ble Commission had recognised that there can be events beyond the control of project developers which warrant regulatory flexibility and exercise of power by this Hon’ble Commission to remove this difficulty and permit commissioning of renewable energy projects. This Hon’ble Commission has also been cognizant of the fact that renewable energy projects ought not to be denied commissioning for reasons beyond their control given that timely addition of renewable energy capacity is also critical for achieving the national energy objectives of the Government of India.

- Additionally, this Hon’ble Commission has passed the following Orders applying the legal principle that generating projects which have been prevented from completing pre-commissioning/commissioning activities for reasons beyond their control, ought to be permitted extension in time for injection of infirm power such that the projects are not left stranded:-

(a)	Order dated 23.10.2024 in Petition No. 386/MP/2024 titled THDC India Ltd. v. Grid Controller of India Ltd.

(b)	Order dated 31.05.2016 in Petition No. 65/MP/2016 titled Ind-Barath Energy (Utkal) Ltd. V. Eastern Regional Load Despatch Centre;

(c)	Order dated 23.03.2026 in Petition No. 91/MP/2026 titled Ayana Renewable Power Four Private Ltd. (ARPFPL) v. Western Regional Load Dispatch Centre (WRLDC).

- It is submitted that the present case stands upon a stronger footing as in the present case, the impediment was the physical collapse of the sole evacuation line of the Project, being a supervening event which is manifestly and completely beyond the control of the Petitioner. Further, and in common with the other cases, the Petitioner has already commissioned the majority of the capacity taken up, being 98.7 MW out of 109.2 MW, with only five Wind Turbine Generators aggregating 10.5 MW remaining for the repeat trial run. Accordingly, it is submitted that this Hon’ble Commission ought to exercise powers under Regulation 57 and grant an extension of 4 months from the date of the Order for injection of infirm power.

D.	Without prejudice, the present Petition is a fit case for the exercise of the Power to Remove Difficulty under Regulation 58 read with Regulation 60 of the IEGC, 2023.

- Without prejudice to the foregoing submissions, it is submitted that a genuine difficulty has arisen in giving effect to Regulation 19 of the IEGC 2023 given that Respondent No. 1/ SRLDC cannot extend the period beyond 135 days and the Petitioner has been kept by Force Majeure from testing within that period.

- Pertinently, this Hon’ble Commission has, on more than one occasion, invoked Regulation 58, read with Regulation 60, to resolve difficulties of precisely this character concerning the injection of infirm power and the conduct of trial runs by renewable projects, as is evident from its Removal of Difficulties Orders dated 30.09.2023 and 18.12.2023 and its Order dated 22.12.2024 in Petition No. 11/SM/2024. Inasmuch as Regulation 58 contemplates the exercise of the said power either upon the Commission’s own motion or upon an application made by the nodal agency, the Petitioner respectfully places the difficulty on record and invites this Hon’ble Commission to exercise the said power suo motu.

- It is submitted that, in seeking the reliefs aforesaid, the Petitioner does not call upon this Hon’ble Commission to rewrite Regulation 19 or to grant any general or blanket dispensation; the Petitioner seeks no more than a case-specific exercise of the powers already conferred upon this Hon’ble Commission by Regulations 19(3), 57 and 58, strictly confined to the five WTGs identified hereinabove. It is a settled principle that a power to relax, or a power to remove difficulty, is to be employed to relieve hardship within the framework of the regulations, and not to alter or supplant their basic scheme; and it is precisely such limited and confined relief, that the Petitioner seeks in the present case.

E.	No prejudice will be caused to any party, and the balance of convenience and the must-run status of renewable energy all favour the relief.

- It is submitted that the extension sought by the Petitioner will occasion no prejudice whatsoever to any party. The Project is a must-run renewable generating station, awarded pursuant to a central competitive bidding process and is supplying power under a subsisting Power Purchase Agreement with SECI. Further, of the entire Project capacity, 98.7 MW already stands in commercial operation,  the repeat trial run to be conducted only for the balance 10.5 MW , and the remaining 70.8 MW will be commissioned progressively.

- It is pertinent to note that SECI has itself extended the Scheduled Commissioning Date by Amendment No. 3 dated 11.05.2026 and the tariff of the Project will remain wholly unaffected. It is submitted that refusal of the relief sought would serve only to strand clean and ready capacity for no fault of the Petitioner and to the benefit of no one. The grant of the extension, would permit the completion of the pre-COD testing and the timely integration of the balance capacity into the grid, which is the very outcome that the IEGC 2023 is designed to achieve.

- It is submitted that this very consideration has weighed decisively with this Hon’ble Commission in the orders noticed hereinabove, each of which records, as the governing rationale for the grant of relief, that “RE capacity, which is ready to be charged and start generation, should not be stranded”. That rationale applies to the facts of the present case with even greater force. It is further submitted that the Petitioner has approached this Hon’ble Commission with promptitude, with clean hands, and upon a full disclosure of all material facts, and that no delay, laches or acquiescence whatsoever is attributable to it.

- In view of the foregoing, it is respectfully submitted that the reliefs prayed for in the present Petition ought to be granted.

- Matters not previously filed or pending with any other court

- It is submitted that no other matter has been filed by the Petitioner raising the issues mentioned in the present Petition, or otherwise on the same cause of action, before this Hon’ble Commission or any other court, tribunal or forum.

- The present Petition is made bona fide and in the interest of justice, and is not barred by any law. The Petitioner craves leave to amend, alter, add to or modify any of the aforesaid grounds and submissions, which are in the alternative and without prejudice to one another, as and when necessary.

- Relief(s) sought

- In view of the aforesaid facts and circumstances and the governing regulatory framework, the Petitioner respectfully prays that this Hon’ble Commission may be pleased to: —

  - Allow the present Petition;

  - Grant an extension of time of 4 (four) months under Regulation 19(3) of the IEGC 2023 from the date of the Order for the injection of infirm power in respect of the balance 5 Wind Turbine Generators aggregating 10.5 MW, namely KKBKA035, KKBKA065, KKBKA112, KKBKA300 and KKBKA305, forming part of the Petitioner’s 180 MW ISTS-connected Kanakagiribad Wind Power Project at Koppal, Karnataka under SECI Tranche-XI given that the Petitioner was prevented from completing trial run solely on account of supervening events beyond the control of the Petitioner;

  - Condone and/or relax the delay in filing of the present Petition in the exercise of the Power to Relax under Regulation 57 of the IEGC 2023 read with Regulation 65 of the CERC (Conduct of Business) Regulations, 2023

  - Exercise its Power to Relax under Regulation 57 of the IEGC, 2023, to relax the provisions of the IEGC 2023 and permit the Petitioner to inject infirm power for the foregoing named 5 WTGs for a period of 4 months from the date of the Order;

  - Alternatively, exercise its Power to Remove Difficulty under Regulation 58 read with Regulation 60 of the IEGC, 2023, on its own motion, to remove the difficulty in giving effect to the provisions and objectives of the IEGC, 2023 in the facts of the present case and permit the Petitioner to inject infirm power for the foregoing named 5 WTGs for a period of 4 months from the date of the Order;

  - Direct Respondent No. 1 to extend the FTC approvals for the 5 WTGs for the period allowed by this Hon’ble Commission and permit the Petitioner to inject infirm power in respect of the said balance capacity and to process the requisite trial-run and operational permissions in accordance with the orders of this Hon’ble Commission; and

  - pass such other order or orders as this Hon’ble Commission may deem fit and proper in the facts and circumstances of the present case, in the interest of justice and equity.

- List of enclosures

As per the Index of Enclosures.

- Proof of Payment

The requisite filing fee of Rs. ____________ has been paid online on ____ / 07 / 2026 bearing Reference No. ____________________.

Sembcorp Green Infra Limited / Petitioner

Through

TRILEGAL

Counsel for the Petitioner

Place: New Delhi

Date: ____ / 07 / 2026